## University Park
UNIVERSITY PARK CAMPUS 2019
BUILDING NAME | PSU Proj.# | Permit # | Bldg.# | Description | Status | Date Sent to L&I | Date Returned | Level of Permit | Design Services / Outside Designer
3035 Research Drive | 00-06715.00 | 201901028 | 0912-000 | Palmer Museum Swing Space | Building Permit | 2019-07-23 | 2019-09-16 | 2 | OD | Christie Holloway |  | Ben
Ag Admin | 02-72197.00 | 201900705 | 0112-000 | Service Entrance Replacement | C of O | 2019-06-04 | 2019-07-02 | 2 | OD | Nate Patrick |  | Ben
Ag Engineering | 00-03437.00 | 201900657 | 0114-000 | Rm 120 ME & ELEC Improvements | Building Permit | 2019-05-16 | 2019-06-21 | 2 | OD | Jeff Spackman |  | Ben
Ag Analytical Services | 00-06838.00 | 201900861 | 0180-004 | Soils Lab Alterations Ph 1 | Building Permit | 2019-07-12 | 2019-08-12 | 2 | OD | Morgan VanOuse |  | Tom Lang
Ag Analytical Services | 00-06838.00 | 201991233 | 0180-004 | Soils Lab Alterations Ph 2 | Building Permit |  | 2019-10-04 | 1 | OD | Morgan VanOuse
Ag Hill Chiller Bldg | 00-05889.00 | 201901191 | 0941-000 | Fit-out for Hydronics Group | Building Permit |  | 2019-10-21 | 2 | OD | Ron Perttu
Ag Science | 00-05321.00 | 201900106 | 0116-000 | Henning Swing Space | C of O |  | 2019-01-28 | 2 | OD | Jeff Spackman
Ag Science | 00-05321.00 | 201900334 | 0116-000 | Henning Swing Space PH 3 Revision | C of O | 2019-03-18 | 2019-04-01 | 2 | OD | Jeff Spackman
Ag Science | 00-05321.00 | 201900762 | 0116-000 | Henning Bldg Connection Alteration | C of O |  | 2019-07-19 | 2 | OD | Jeff Spackman
Althouse Lab | 00-06777.00 |  | 0411-000 | Room 8 Alterations | Rejected | 2019-03-28 | 2019-04-15 | 1 | OD | Jason Smith
Althouse Lab | 00-06777.00 | 201900630 | 0411-000 | Rm 8 Alterations | C of O |  | 2019-06-18 | 2 | OD | Jason Smith
Arboretum - Hoop Arbor | 00-06273.00 | 201901107 | 0995-130/3 | New Structure | Building Permit |  | 2019-10-11 | 2 | OD | Jude Larkin
Arboretum - Trellis Arch 1 | 00-06273.00 | 201901109 | 0995-130/3 | New Structure | Building Permit |  | 2019-10-11 | 2 | OD | Jude Larkin
Arboretum - Trellis Arch 2 | 00-06273.00 | 201901110 | 0995-130/3 | New Structure | Building Permit |  | 2019-10-11 | 2 | OD | Jude Larkin
Arboretum - Bee Hive | 00-06273.00 | 201901106 | 0995-130/3 | New Structure | Building Permit |  | 2019-10-11 | 2 | OD | Jude Larkin
Arboretum - Bird House | 00-06273.00 | 201901112 | 0995-130/3 | New Structure | Building Permit |  | 2019-10-11 | 2 | OD | Jude Larkin
Arboretum - Overlook Pavillion | 00-06273.00 | 201901111 | 0145-001 | Lighting System Upgrades | Building Permit |  | 2019-10-11 | 2 | OD | Jude Larkin
Arboretum - Viewing Pavillion | 00-06273.00 | 201901108 | 0145-002 | New Structure | Building Permit |  | 2019-10-11 | 2 | OD | Jude Larkin
ARL Test Track Bldg 1 | 00-05194.00 | 201900242 | 0996-015 | Power Supply for Saw Shed | Building Permit |  | 2019-03-07 | 2 | OD | Jeff Spackman
ARL Test Track Bldg 3 | 05194/06627 | 201900284 | N/A | New Structure | Building Permit | 2019-02-11 | 2019-03-22 | 2 | OD | Jeff Spackman
ARL Test Track Bldg 3 | 05194/06627 | 201901041 | N/A | New Structure - Fire Alarm | Building Permit |  | 2019-09-20 | 2 | OD | Jeff Spackman
ARL Saw Shed, Test Track Bldg 4 | 05194/06627 | 201900241 | N/A | New Structure - Saw Shed | Building Permit | 2019-02-11 | 2019-03-07 | 2 | OD | Jeff Spackman
ARL West I | 00-06012.00 | 201900578 | 0996-019 | Supplementary Heating and Cooling | Building Permit | 2019-05-06 | 2019-06-06 | 2 | OD | Jeff Spackman
ARL West II | 00-06012.02 | 201900674 | 0065-000 | High Pressure Pump | C of O | 2019-05-23 | 2019-06-26 | 2 | OD | Jeff Spackman
ARL West III | 00-06688.00 | 201900343 | 0066-000 | High Temp Furnace | Building Permit | 2019-03-11 | 0404/19 | 2 | OD | Jeff Spackman
ARL West III | 00-06728.00 | 201900312 | 0066-000 | Rooftop Unit Replacement | Building Permit | 2019-03-27 | 2019-03-28 | 2 | OD | Damian Rose
Beecher Dock House | 00-05489.01 |  | 0665-000 | Partial Basement Reno | PEnding | 2019-12-17 |  | 2 | DS | Ron Perttu | Forrest Rishel
Borland | 00-06067.00 | 201900459 | 0107-000 | Room 113 Reno | C of O | 2019-03-29 | 2019-05-02 | 2 | OD | Monica Reed |  | Ben Bidelspach
Boucke | 00-06291.00 | 201900234 | 0013-000 | Office 120 & 121 Reno | C of O | 2019-01-21 | 2019-03-07 | 2 | OD | Derek Leonard
Brumbaugh Hall | 00-05289.00 | 201900030 | 0257-000 | Building Reno - Ph 1C Fire Alarm | C of O | 2018-11-09 | 2019-01-15 | 2 | OD | Rich O'Donald
Bryce Jordan Center | 00-05500.00 | 201900351 | 0045-000 | HVAC Reno Ph 5 | C of O |  | 2019-04-08 | 2 | OD | Nate Patrick
Bryce Jordan Center | 00-06980.00 | 201900720 | 0045-000 | Food Service Refrigeration Unit | C of O | 2019-06-12 | 2019-07-09 | 2 | OD | Alan Zimmerman |  | Ben
Business Bldg | 00-06692.00 | 201901291 | 0023-001 | Recruiter Lounge 337A | Building Permit | 2019-10-28 | 2019-11-21 | 2 | DS | Julie Patrick | Forrest Rishel | Ben
Carpenter | 00-07044.00 | 201901238 | 0453-000 | Modern DNA Lab Suites 401 & 401A | Building Permit |  | 2019-11-01 | 2 | OD | Chad Spackman |  | Ben
Centralized Biological Lab | 00-06730.00 | 201901448 | 0404-000 | Cage Wash Reno | Building Permit | 2019-12-09 | 2020-01-03 | 2 | OD | Morgan VanOuse
Chemistry | 00-06051.00 |  | 0050-000 | Rm 527A Fume Hood Install | Cancelled | 2019-05-22 |  | 2 | DS | Monica Reed | Pete, Adam
College Heights Elementary | 00-04941.00 | 201900033 | 0999-520 | Building Reno | C of O | 2018-12-19 | 2019-01-21 | 2 | OD | Chad Spackman
College Heights Elementary | 00-04941.00 | 201900296 | 0999-520 | Bldg Reno Construction Type & Accessiblity Rev | C of O | 2019-02-25 | 2019-03-28 | 2 | OD | Chad Spackman
Dairy Administration | 08-72602.05 | 201900202 | 0168-001 | Fire Alarm Revision | C of O |  | 2019-03-01 | 2 | OD | Jeff Spackman
Dairy Barn E | 08-72602.05 | 201900201 | 0168-005 | Fire Alarm Revision | C of O |  | 2019-03-01 | 2 | OD | Jeff Spackman
Dairy Barn F | 08-72602.05 | 201900203 | 0168-006 | Fire Alarm Revision | C of O |  | 2019-03-01 | 2 | OD | Jeff Spackman
Davey lab | 00-06333.00 | 201900617 | 0412-000 | Incremental Renewal Master Plan Ph 1 | Building Permit | 2019-05-08 | 2019-06-12 | 2 | DS | Jessica Dubler | Adam Davis
Deike | 00-05846.00 | 201900332 | 0503-000 | Basement Level Demo | C of C | 2019-03-12 | 2019-03-28 | Demo | OD | Dave Peck
Deike | 00-06220.00 |  | 0503-000 | Lab 420, 422, 423 & 431 HVAC Revision | Rejected | 2019-10-01 | 2019-10-29 | 2 | OD | Dave Peck
Deike | 00-06220.00 | 201901337 | 0503-000 | Lab 420, 422, 423 & 431 HVAC Revision Resubmission | Building Permit | 2019-11-08 | 2019-12-12 | 2 | OD | William Waugh |  | Ben
Eisenhower Chapel | 00-05372.00 | 201900457 | 0006-000 | Piping Replacement | C of O | 2019-04-04 | 2019-05-02 | 2 | OD | Derek Leonard
Electrical Engineering East | 00-06530.00 | 201900265 | 0315-000 | Lab 329 Reno | C of O | 2019-02-25 | 2019-03-15 | 2 | OD | Dwayne Rush
Electrical Engineering West | 00-06529.00 | 201900288 | 0302-000 | Lab 301 Reno | C of O | 2019-02-25 | 2019-03-22 | 2 | OD | Dwayne Rush
Elliot Building | 00-06275.00 | 201900222 | 0034-001 | Rm 110 Reno Sprinkler | C of O | 2019-02-13 | 2019-03-01 | 2 | OD | Brian Hayes
Elliot Building | 00-06701.00 | 201900357 | 0034-001 | Office of Strategic Communication | C of O | 2019-03-18 | 2019-04-08 | 2 | OD | Brian Hayes
Elliot Building | 00-06701.00 | 201901017 | 0034-001 | Strategic Communication Office Sprinklers | Building Permit |  | 2019-09-13 | 2 | OD | Brian Hayes
Elliot Building | 00-06701.00 | 201901077 | 0034-001 | Strategic Communication Office Fire Alarm | Building Permit |  | 2019-10-04 | 2 | OD | Brian Hayes
Fisher Hall | 00-06168.00 | 201900825 | 0260-000 | Ph 2A Basement Reno - Fire Alarm | C of O |  | 2019-08-07 | 2 | OD | Rich O'Donald
Fisher Hall | 00-06168.00 | 201900872 | 0260-000 | Ph 2A Basement Reno - Sprinkler | C of O |  | 2019-08-13 | 2 | OD | Rich O'Donald
Fisher Hall | 00-06168.00 | 201900935 | 0260-000 | Ph 2A Basement Reno Revision | Building Permit |  | 2019-08-28 | 2 | OD | Rich O'Donald
Fleet Operations Facility | 00-05738.00 | 201901329 | 0903-000 | Upgrade Office Spaces | Building Permit | 2019-11-08 | 2019-12-09 | 2 | DS | kurt coduti | Scot Miller
Food Sciences | 00-06095.00 |  | 0107-001 | Silo Pit Safety Improvements | Rejected | 2019-11-01 |  | 1 | DS | Morgan VanOuse | Kathy Poissant
Food Sciences | 00-06095.00 | 202000001 | 0107-001 | Silo Pit Safety Improvements | Building Permit | 2019-12-12 | 2020-01-07 | 2 | DS | Morgan VanOuse | Kathy Poissant
Garfield Water Tunnel | 00-06225.00 | 201900336 | 0996-011 | Sump Pump Rev | C of O |  | 2019-04-08 | 2 | OD | Jeff Spackman
Garfield Water Tunnel | 00-04270.00 | 201900859 | 0996-011 | Motor-Generator Set Upgrade | Building Permit | 2019-07-03 | 2019-08-12 | 2 | OD | Jeff Spackman | Ben Bidelspach
Geary Hall | 00-06168.00 | 201900224 | 0246-000 | Building Reno - Ph 2A | Building Permit |  | 2019-03-07 | 2 | OD | Rich O'Donald
Geary Hall | 00-06168.00 | 201900990 | 0246-000 | Building Reno Ph 2A Revisions | Building Permit |  | 2019-09-10 | 2 | OD | Rich O'Donald
Geary Hall | 00-06168.00 | 201901293 | 0246-000 | Building Reno - Ph 2A Fire Alarm | Building Permit |  | 2019-11-21 | 2 | OD | Rich O'Donald
Geary Hall | 00-06168.00 | 201901246 | 0246-000 | Building Reno - Ph 2A Sprinkler | Building Permit |  | 2019-11-07 | 2 | OD | Rich O'Donald
General Aviation Admin Carport | 00-05807.00 | 201900509 | 0963-017 | Carport Installation | Building Permit | 2019-04-08 | 2019-05-17 | 2 | OD | kurt coduti | Chris Musser
Greenburg Indoor Sports Complex | 00-06971.00 | 201900675 | 0835-000 | Ground Floor Swing Space Reno | C of O | 2019-05-20 | 2019-06-26 | 2 | OD | Jason Anderson
Hallowell | 00-06955.00 |  | 0317-000 | Suite 305 Ancient DNA Lab | Pending | 2019-12-20 |  | 2 | OD | Chad Spackman
Hamilton Hall | 00-06401.00 | 201900372 | 0205-000 | Bathroom Reno Ph 1 | C of O | 2019-03-13 | 2019-04-11 | 2 | OD | Rich O'Donald
Henderson South | 00-06517.00 | 201900105 | 0652-000 | Room 357 Reno | Building Permit |  | 2019-01-28 | 2 | OD | Christie Holloway
Henning | 00-05321.00 | 201900759 | 0115-000 | Building Demo | C of C | 2019-06-26 | 2019-07-19 | 2 | OD | Jeff Spackman
Henning Building Replacement | 00-05321.00 | 201900923 | 0119-000 | Foundation | Building Permit |  | 2019-08-22 | 2 | OD | Jeff Spackman |  | Ben
Horse Barn | 0-06544.00 | 201900979 | 0126-000 | Renovations to Room 105 | Building Permit | 2019-07-13 | 2019-09-06 | 2 | DS | Jeff Spackman | Deb Fuller
Hosler | 00-06881.00 | 201901120 | 0502-000 | Main Switchboard Replacement | Building Permit | 2019-09-06 | 2019-10-10 | 2 | DS | William Waugh | Brian Brubaker
HUB | 00-06430.00 | 201900378 | 0005-000 | Sbarro Restaurant Reno | C of O | 2019-03-19 | 2019-04-12 | 2 | OD | Matt Vail
HUB | 00-06151.00 | 201900510 | 0005-000 | Robeson Gallery Reno for LGBTQA | Building Permit | 2019-04-03 | 2019-05-17 | 2 | DS | Chad Spackman | Kathy Poissant
HUB | 00-06151.00 | 201901302 | 0005-000 | Restroom R012 & R013 Reno | Building Permit | 2019-11-01 | 2019-12-02 | 2 | DS | Chad Spackman | Kathy Poissant
HUB | 00-06773.00 | 201901036 | 0005-000 | Renovate Breakzone | Building Permit | 2019-08-08 | 2019-09-18 | 2 | DS | Derek Leonard | Debbie Fuller
Irvin Hall | 00-05994.00 | 201901438 | 0203-000 | Stair Renovations | Building Permit |  | 2020-01-03 | 2 | OD | Jason Anderson |  | Ben Bidelspach
James Bldg | 00-06403.00 | 201900884 | 0998-027 | Building Demolition | Demo Permit |  | 2019-08-21 | DEMO | OD | Dave Peck
James Bldg Replacement | 00-06403.00 | 201901187 | 0054-000 | Foundation Only | Building Permit | 2019-10-03 | 2019-10-21 | 2 | OD | Dave Peck
James Bldg Replacement | 00-06403.00 | 201901418 | 0054-000 | New Structure | Building Permit | 2019-11-21 | 2019-01-02 | 2 | OD | Dave Peck
Johnston Commons | 00-05289.00 | 201900032 | 0276-000 | Phase 1C Office Reno | Building Permit | 2018-12-15 | 2019-01-15 | 2 | OD | Rich O'Donald
Johnston Commons | 00-05289.00 | 201900608 | 0276-000 | Phase IC Rest Room Partial Occupancy | Building Permit | 2019-05-21 | 2019-06-10 | 2 | OD | Rich O'Donald
Johnston Commons | 00-05289.00 | 201900607 | 0276-000 | Phase 1C Office Reno - Fire Alarm | Building Permit |  | 2019-06-11 | 2 | OD | Rich O'Donald
Johnston Commons | 00-05289.00 | 201900609 | 0276-000 | Phase 1C Office Space Partial Occupancy | Building Permit | 2019-05-21 | 2019-06-11 | 2 | OD | Rich O'Donald
Johnston Commons | 00-06168.00 | 201901149 | 0276-000 | Phase 2A Reno Tunnel Revisions | Building Permit |  | 2019-10-17 | 2 | OD | Rich O'Donald
Johnston Commons | 00-06750.00 | 201901406 | 0276-000 | Phase 2B Renovations | Building Permit | 2019-11-13 | 2019-12-19 | 2 | OD | Rich O'Donald
Katz | 00-06809.00 | 201900563 | 0991-200 | Office Suites Reno | C of O | 2019-04-12 | 2019-05-31 | 2 | OD | Dwayne Rush
Katz | N/A | 201900476 | 0991-200 | Panera Bread Fit-out | C of O |  | 2019-05-07 | 2 | OD | Matt Vail
Kern | 00-03448.00 | 201900067 | 0452-000 | Graduate School Reno 1st & 2nd Flr | Building Permit |  | 2019-01-25 | 2 | OD | Jason Smith
Kern | 00-03448.00 | 201900635 | 0452-000 | Graduate School Reno Partial Occupancy | C of O | 2019-05-15 | 2019-06-20 | 2 | OD | Jason Smith |  | Ben
Kern | 00-03448.00 | 201901295 | 0452-000 | Grad School Reno - Conference Rm 116 Partial Occup | Building Permit |  | 2019-11-21 | 2 | OD | Jason Smith |  | Ben
Kern | 00-03448.00 | 201901292 | 0452-000 | Grad School Reno - Lobby/Offices Partial Occupancy | Building Permit |  | 2019-11-21 | 2 | OD | Jason Smith |  | Ben
Kern | 00-03448.00 | 201901296 | 0452-000 | Grad School Reno - 2nd Flr Partial Occupancy | Building Permit |  | 2019-11-21 | 2 | OD | Jason Smith |  | Ben
Kern | N/A | 201900475 | 0452-000 | Panera Bread Fit-out | C of O |  | 2019-05-07 | 2 | OD | Matt Vail |  | Ben
Lasch | 00-06552.00 | 201900122 | 0845-000 | Players Lounge Revision | C of O | 2019-01-21 | 2019-02-04 | 2 | OD | Marv Bevan
Lasch | 00-06552.00 | 201900247 | 0845-000 | Players Lounge Sprinkler | Building Permit |  |  | 2 | OD | Marv Bevan
Mateer | 00-06506.00 | 201901393 | 0667-000 | Suite 201 New Office | Building Permit | 2019-11-21 | 2019-12-17 | 2 | DS | Christie Holloway | Forrest Rishel | Ben
Material Research Institute | 00-06414.01 | 201900157 | 0965-002 | Lab 129 Fitout | C of O | 2019-01-25 | 2019-02-15 | 2 | OD | Jason Smith
Millenium Science | 00-07077.01 | 201901089 | 0038-001 | First Floor Electrical Upgrades | Building Permit | 2019-08-30 | 2019-10-07 | 2 | OD | Jason Smith |  | Ben
Millenium Science | 00-07077.02 | 201901092 | 0038-001 | Basement Electrical Upgrades | Building Permit | 2019-08-30 | 2019-10-07 | 2 | OD | Jason Smith |  | Ben
McElwain | 00-06518.00 | 201900324 | 0240-000 | Water heater | C of O |  | 2019-03-28 | 2 | OD | Matt Vail
Meats Lab | 00-05635.00 | 201900223 | 0128-000 | HVAC Upgrades | C ofO |  | 2019-03-12 | 2 | OD | Matt Norris P&E
Medlar Field | 00-05891.00 | 201900544 | 0827-000 | Cellular Power at Scoreboard | C of O | 2019-04-16 | 2019-05-28 | 2 | DS | Jason Anderson | Brian Brubaker
Mueller | 00-06332.00 | 201900210 | 0409-000 | 409, 410, 419 HVAC Reno | C of O | 2019-02-08 | 2019-02-28 | 2 | DS | Jessica Dubler | Jim Rohan
Mueller | 00-07112.00 |  | 0409-000 | 217B Office Reno | PEnding | 2019-12-11 |  | 2 | OD | Jason Anderson
Nittany Lion Inn | 00-07283.00 | 201991660 | 0091-000 | Fireplace Reno | Building Permit | 2019-11-19 | 2019-12-09 | 1 | DS | Jason Anderson
North American Refractories | 00-06640.00 | 201900037 | 0064-000 | Air Compressor Replacement | C of O | 2018-12-20 | 2019-01-17 | 2 | DS | Dwayne Rush
North American Refractories | 00-07003.00 | 201900899 | 0064-000 | Start Lab Dynamometer Modifications | Building Permit | 2019-07-17 | 2019-08-19 | 2 | OD | Dwayne Rush
Nittany Parking Deck | 00-05774.00 | 201900044 | 0995-060 | Ventilation Upgrades | C of O | 2018-12-03 | 2019-01-21 | 2 | OD | Kurt Coduti
Old Main | 00-06871.00 | 201901095 | 0001-000 | ACF-4 & Ventilation Improvements | Building Permit |  | 2019-10-04 | 2 | OD | Marv Bevan |  | Ben
Pattee | 00-05803.00 | 201900120 | 0003-000 | West Interior Courtyard Infill - Fire Alarm | C of O |  | 2019-02-05 | 2 | OD | Chad Spackman
Pattee | 00-05803.00 | 201900238 | 0003-000 | West Interior Courtyard Infill - Sprinkler | Building Permit | 2019-02-11 | 2019-04-12 | 2 | OD | Chad Spackman
Pattee | 00-05803.00 | 201900401 | 0003-000 | West Interior Courtyard Infill - Ground Flr Revisions | Building Permit |  | 2019-04-18 | 2 | OD | Chad Spackman
Pattee | 00-05803.00 | 201900461 | 0003-000 | West Interior Courtyard Infill - Partial Occupancy #1 | C of O |  | 2019-05-07 | 2 | OD | Chad Spackman
Pattee | 00-05803.00 | 201900462 | 0003-000 | West Interior Courtyard Infill - Partial Occupancy #2 | C of O |  | 2019-05-07 | 2 | OD | Chad Spackman
Pattee | 00-05803.00 | 201900794 | 0003-000 | West Reno Ph3 Immersive Lab Fire Alarm | C of O |  | 2019-07-31 | 2 | OD | Chad Spackman
Pattee | 00-05803.00 | 201900865 | 0003-000 | W. Reno Ph3 Immersive Lab Sprinkler (drawings only) | Building Permit |  |  | 2 | OD | Chad Spackman
Pattee | 00-05803.00 | 201901398 | 0003-000 | Automatic Transfer Switch Work | C of O |  | 2019-12-18 | 2 | OD | Chad Spackman
Pattee | 00-06810.00 | 201900528 | 0003-000 | Assessment Office Reno | Building Permit | 2019-04-12 | 2019-05-28 | 2 | OD | Derek Leonard
Pegula Ice Arena | 00-06440.00 | 201900003 | 0829-000 | Thermosyphon Vessel Replacement | Building Permit | 2018-12-04 | 2019-01-07 | 2 | OD | Marv Bevan
Pegula Ice Arena | N/A | 201990980 | 0829-000 | Duck Donut Fit-out | Building Permit |  | 2019-08-21 | 1 | OD | None Assigned
Pegula Ice Arena | 00-06760.00 | 201901082 | 0829-000 | AT&T Distributed Antenna System | Building Permit |  | 2019-10-03 | 2 | OD | Jason Anderson |  | Tom
Pell Lab | 00-06550.00 | 201900215 | 0169-020 | Mechanical Canopy | C of O | 2019-02-12 | 2019-02-28 | 2 | OD | Alan Zimmerman
Pell Lab | 00-06550.00 | 201900624 | 0169-020 | Mechanical Canopy Revision | C of O | 2019-05-09 | 2019-06-18 | 2 | OD | Alan Zimmerman
Pinchot Hall | 00-05289.00 | 201900029 | 0259-000 | Building Reno - Ph 1C Fire Alarm | C of O | 2018-11-09 | 2019-01-15 | 2 | OD | Rich O'Donald
Pollock Commons | 00-05459.00 | 201900177 | 0275-000 | Market and Café Reno | C of O |  | 2019-02-20 | 2 | OD | Rich O'Donald
Pollock Commons | 00-05459.00 | 201900869 | 0275-000 | Market and Café Reno - Fire Alarm | C of O |  | 2019-08-13 | 2 | OD | Rich O'Donald
Pollock Commons | 00-05459.00 | 201900742 | 0275-000 | Market and Café Reno - Sprinkler (drawings only) | Building Permit |  |  | 2 | OD | Rich O'Donald
Power Plant (W. Campus Steam Plant) | 00-04966.00 | 201901267 | 0911-000 | Bldg Expansion and Substations - Foundation | Building Permit |  | 2019-11-12 | 2 | OD | Jeff Spackman |  | Ben
Reber | 00-07140.00 | 201901391 | 0303-000 | Rm 315 Fume Hood | Building Permit | 2019-11-20 | 2019-12-17 | 2 | DS | Bill Waugh | Adam Davis | Ben
Research Bldg East | 00-06735.00 | 201901417 | 0028-000 | Rms 218 & 222 Lab Reno | Building Permit |  | 2019-01-02 | 2 | OD | Brian Hayes
Research Bldg West | 00-06012.01 | 201900671 | 0271-000 | ARL Laser Lab Heating and Cooling | C of O | 2019-05-22 | 2019-06-21 | 2 | OD | Jeff Spackman
Research Bldg West | 00-06012.03 | 201901118 | 0271-000 | Rm 68 Instron Unit Install | Building Permit | 2019-09-10 | 2019-10-10 | 2 | OD | Jeff Spackman |  | ben
Research Bldg West | 00-06974.00 | 201901244 | 0271-000 | Utilities for Sintering System | Building Permit | 2019-10-11 | 2019-11-07 | 2 | DS | Bill Waugh | Bob Zakrzwski | Ben
Ritenour | 00-05724.00 | 201900370 | 0051-000 | Veterans Affairs Services | Building Permit |  | 2019-04-13 | 2 | OD | Ron Perttu
Ritenour | 00-05724.00 | 201900827 | 0051-000 | Veterans Affairs Services - Partial Occupancy | C of O |  | 2019-08-05 | 2 | OD | Ron Perttu
Ritenour | 00-05724.00 | 201900506 | 0051-000 | Veterans Affairs Sprinklers and Fire Alarm | Building Permit |  | 2019-05-17 | 2 | OD | Ron Perttu
Ritenour | 00-05724.00 | 201900908 | 0051-000 | Reno for Millennium Scholars | Building Permit |  | 2019-08-22 | 2 | OD | Ron Perttu
Ritenour | 00-05724.00 | 201901155 | 0051-000 | Reno for Millennium Scholars - Sprinkler & Fire Alarm | Building Permit | 2019-10-02 | 2019-10-17 | 2 | OD | Ron Perttu
Solar Home (Morningstar) | 00-06031.00 | 201900511 | 0326-000 | Roof Replacement | Building Permit |  | 2019-05-17 | 2 | OD | Christie Holloway | Dan Aumiller
Sparks | 00-06250.00 | 201900847 | 0701-000 | Single User Restroom | C of O | 2019-06-27 | 2019-08-06 | 2 | DS | Derek Leonard | Kathy Poissant
Sproul Hall | 00-06168.00 | 201900230 | 0258-000 | Bldg Reno - Ph 2A | Building Permit |  | 2019-03-07 | 2 | OD | Rich O'Donald
Sproul Hall | 00-06168.00 | 201900983 | 0258-000 | Bldg Reno Ph 2A Revisions | Building Permit |  | 2019-09-10 | 2 | OD | Rich O'Donald
Sproul Hall | 00-06168.00 | 201901245 | 0258-000 | Bldg Reno Ph 2A Sprinkler | Building Permit |  | 2019-11-07 | 2 | OD | Rich O'Donald
Steam Services Bldg | 08-93143.02 | 201900194 | 0911-000/7 | New Structure Sprinkler | Building Permit |  |  | 2 | OD | Jeff Spackman
Steam Services Bldg | 08-93143.02 | 201900272 | 0911-000/7 | New Structure Sprinkler Standpipe Revision | Building Permit |  |  | 2 | OD | Jeff Spackman
Steam Services Bldg | 08-93143.02 | 201900467 | 0911-000/7 | New Structure - Fire Alarm | C of O |  | 2019-05-06 | 2 | OD | Jeff Spackman
Telecommunications Bldg | 00-0684500 | 201900755 | 0020-000 | Single User Restroom and Main Entrance power door | Building Permit | 2019-05-21 | 2019-07-18 | 2 | DS | Ron Perttu | Scott Miller
Tener Hall | 00-05289.00 | 201900026 | 0256-000 | Building Renovation - Ph 1C Fire Alarm | Building Permit | 2018-11-09 | 2019-01-15 | 2 | OD | Rich O'Donald
Test Track Office | 00-04777.00 | 201900623 | 0196-002 | New Entrance Canopy | Building Permit | 2019-05-09 | 2019-06-18 | 2 | OD | Alan Zimmerman
Theatre Arts (Music 1) | 00-04917.00 | 201900603 | 0751-000 | Bldg Reno & Add - Fire Pump Reno - Fire Alarm | Building Permit |  | 2019-06-10 | 2 | OD | Rachel Prinkey
Thomas | 00-05743.01 | 201900091 | 0040-000 | Basement Swing Space Reno | C of O | 2019-01-11 | 2019-01-25 | 2 | OD | Jason Anderson
Thomas | 00-05743.01 |  | 0040-000 | Basement Swing Space - Fire Alarm Revision | Pending | 2019-04-17 |  | 2 | OD | Jason Anderson
Thomas | 00-05743.01 | 201900556 | 0040-000 | Basement Swing Space - Sprinkler Revision | C of O | 2019-04-17 | 2019-05-28 | 2 | OD | Jason Anderson
Tyson | 00-06177.01 | 201900019 | 0110-000 | Lab 107 HVAC Modifications | C of O | 2018-11-29 | 2019-01-10 | 2 | OD | Jeff Spackman
USB II | 00-05704.00 | 201900866 | 0193-003 | Suite 112 Reno Revision | Building Permit | 2019-07-10 | 2019-08-12 | 2 | DS | Derek Leonard | Andy Bucha | Steve Merrick
Vehicle Testing Lab | 00-06849.00 | 201900535 | 0196-005 | New Fused Disconnect | Building Permit | 2019-04-12 | 2019-05-22 | 2 | OD | Dave Peck
Visual Arts | N/A | 201900477 | 0754-000 | Panera Bread Fit-out | C of O |  | 2019-05-08 | 2 | OD | Matt Vail
Wagner | 00-06061.00 | 201900303 | 0014-000 | Annex Rooftop Unit Replacement | C of O |  | 2019-03-25 | 2 | DS | Derek Leonard | Jim Rohan
Walker | 00-05610.00 | 201901421 | 0504-000 | Ph2 HVAC Reno | Building Permit | 2019-12-02 | 2020-01-02 | 2 | OD | Alan Zimmerman |  | Ben Bidelspach
WWTP - Delpac Tank | 00-05991.00 | 201900180 | 0994-000 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
WWTP - Odor Control | 00-05991.00 | 201900181 | 0994-032 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
WWTP - Old Lab Bldg | 00-05991.00 | 201900182 | 0994-001 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
WWTP - Sludge Thickener Bldg | 00-05991.00 | 201900183 | 0994-021 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
WWTP - TFP Biofilter Tank | 00-05991.00 | 201900184 | 0994-045 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
WWTP - TFP Recirculation Pump Bldg | 00-05991.00 | 201900185 | 0994-006 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
WWTP - Trickling Filter 1 | 00-05991.00 | 201900186 | 0994-008 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
WWTP - Trickling Filter 2 | 00-05991.00 | 201900187 | 0994-009 | Demolition of Building | C of C |  | 2019-03-01 | Demo | OD | Rachel Prinkey
Water Treatment Plant | 05-92438.00 | 201900976 | 0918-001 | Ancillary Design | Building Permit | 2019-08-12 | 2019-09-10 | 2 | OD | Jeff Kokosky
Westgate | 00-06357.00 | 201900250 | 0039-000 | RM E303 E304 Office Space Reno | C of O | 2019-02-13 | 2019-03-12 | 2 | DS | Derek Leonard | Scott Miller
Westgate (IST) | N/A | 201900479 | 0039-000 | Panera Bread Fit-out | C of O | 2019-05-08 | 2019-05-09 | 2 | OD | Matt Vail
West Campus Parking Deck | N/A | 201901075 | N/A | New Structure | Building Permit |  | 2019-10-03 | 2 | OD | kurt coduti
White | 00-04869.01 | 201900579 | 0802-000 | Room 33 AHU Upgrade Revision | C of O | 2019-05-01 | 2019-06-11 | 2 | DS | Derek Leonard
Whitmore | 00-06368.00 | 201900494 | 0406-000 | 3rd Floor Ventilation Upgrades | C of O |  | 2019-05-15 | 2 | OD | Sam Bertolino
Willard | 00-05743.00 | 201900330 | 0012-000 | Restroom Renovation | C of O | 2019-03-08 | 2018-03-28 | 2 | OD | Monica Reed
Willard | 00-05743.00 | 201900797 | 0012-000 | Foundation to Grade Reno | Building Permit | 2019-04-12 | 2019-07-25 | 2 | OD | Monica Reed
Willard | 00-05743.00 | 201900512 | 0012-000 | Telecom Relocation | Building Permit | 2019-04-12 | 2019-05-17 | 2 | OD | Monica Reed

## Commonwealth
CAMPUS 2019 | PSU PROJECT # | Permit # | BLDG. # | DESCRIPTION | STATUS | DATE SENT | DATE RETURNED | PERMIT LEVEL | DS/OD
ABINGTON CAMPUS 0979-000
Woodland | 00-06145.00 | 201990143 | 0979-008 | Library and Mechanical Rm Roof Replacement | C of C |  | 2019-03-22 | 1 | OD
Woodland | 00-06496.00 | 201900552 | 0979-008 | Classroom 132 Reno | C of O | 2019-04-05 | 2019-05-28 | 2 | OD
Woodland | 00-06496.00 | 201901265 | 0979-008 | Classroom 132 Reno Revision | C of O | 2019-10-23 | 2019-11-11 | 2 | OD
ALTOONA CAMPUS 0974-000
Forced Advanced Technology Center | 00-07071.00 | 201901185 | 0974-019 | Classroom 208 Reno | Building Permit | 2019-08-30 | 2019-10-17 | 2 | OD
Linden Building | 00-06636.00 | 201901117 | 0974-076 | Demolition of Structure | Building Permit | 2019-09-06 | 2019-10-10 | 2 | OD
Sheetz Family Medical Ctr | 00-04787.00 | 201900767 | 0974-070 | Canopy Alterations | Building Permit |  | 2019-07-24 | 2 | OD
Willow Building | 00-06636.00 | 201901116 | 0974-024 | Demolition of Structure | Building Permit | 1833397 | 2019-10-10 | 2 | OD
BEAVER CAMPUS 0986-000
Harmony Hall | 00-06276.00 | 201900913 | 0986-007 | Kitchen Fan Upgrade | Building Permit |  | 2019-08-22 | 2 | OD
Library | 00-05850.00 | 201990477 | 0986-005 | Roof Replacement | C of C | 2019-04-27 | 2019-05-06 | 1 | OD
Library | 00-05850.00 | 201900587 | 0986-005 | Roof Fall Protection | Building Permit |  | 2019-06-10 | 2 | OD
Library | 00-06613.00 | 201900713 | 0986-005 | Seminar Room Reno | Building Permit |  | 2019-07-09 | 2 | OD
Student Union | 00-05851.00 | 201990478 | 0986-010 | Roof Replacement | C of C | 2019-04-27 | 2019-05-06 | 1 | OD
Student Union | 00-05851.00 | 201900583 | 0986-010 | Roof Fall Protection | Building Permit |  | 2019-06-10 | 2 | OD
LCB/GCB Pavilion | 00-05235.00 | 201900766 | 0986-018 | New Construction | Building Permit |  | 2019-07-23 | 2 | OD
BEHREND CAMPUS 0972-000
Glenhill Farmhouse | 00-06621.00 | 201901326 | 0972-001 | Data Closet | C of O | 2019-11-07 | 2019-12-09 | 2 | OD
Reed Hall | 00-05943.00 | 201900036 | 0972-006 | Rooftop Unit & NTS Room Air Conditioning | Building Permit | 2018-12-20 | 2019-01-25 | 2 | OD
Reed Hall | 00-06818.00 | 201901150 | 0972-006 | Bruno's Kitchen A/C Upgrades | Building Permit | 2019-09-16 | 2019-10-17 | 2 | OD
BERKS CAMPUS 0980-000
Perkins Student Center | 00-06729.00 | 201900168 | 0980-005 | RM 10 Dehumidification | Building Permit | 2019-01-28 | 2019-02-19 | 2 | OD
Laurel Hall | 00-06863.00 | 201990549 | 0980-061 | Building Envelope Rehab | C of C | 2019-05-08 | 2019-05-23 | 1 | OD
Luerssen | 00-06719.00 | 201990137 | 0980-004 | Site Lighting Upgrades | Building Permit | 2019-02-22 | 2019-03-22 | 1 | OD
Bowman Residence Center | 00-06719.00 | 201990138 | 0980-060 | Site Lighting Upgrades | Building Permit | 2019-02-22 | 2019-03-22 | 1 | OD
Bowman Residence Center | 00-06863.00 | 201990548 | 0980-060 | Building Envelope Rehab | C of C | 2019-05-08 | 2019-05-23 | 1 | OD
Cedar Hall | 00-06863.00 | 201990554 | 0980-066 | Building Envelope Rehab | C of C | 2019-05-08 | 2019-05-23 | 1 | OD
Greenbrier Hall | 00-06863.00 | 201990553 | 0980-065 | Building Envelope Rehab | C of C | 2019-05-08 | 2019-05-23 | 1 | OD
Oakmoss Hall | 00-06863.00 | 201990550 | 0980-062 | Building Envelope Rehab | C of C | 2019-05-08 | 2019-05-23 | 1 | OD
Woods Residence Hall | 00-06719.00 | 201990139 | 0980-067 | Site Lighting Upgrades | Building Permit | 2019-02-22 | 2019-03-22 | 1 | OD
Athletic Storage Bldg | 00-06719.00 | 201990140 | 0980-070 | Site Lighting Upgrades | Building Permit | 2019-02-22 | 2019-03-22 | 1 | OD
Sage Hall | 00-06863.00 | 201990552 | 0980-064 | Building Envelope Rehab | C of C | 2019-05-08 | 2019-05-23 | 1 | OD
Sweetwood Hall | 00-06863.00 | 201990551 | 0980-063 | Building Envelope Rehab | C of C | 2019-05-08 | 2019-05-23 | 1 | OD
BRANDYWINE CAMPUS 0989-000
Commons Athletic Center | 00-06698.00 | 201900483 | 0989-005 | Entry and Walkway Rehab | Building Permit | 2019-04-08 | 2019-05-13 | 2 | DS
Vairo Library | 00-06565.00 |  | 0989-004 | Exterior Lighting | Rejected | 2019-02-19 | 2019-03-07 | 1 | OD
Vairo Library | 00-06565.00 | 201990136 | 0989-004 | Exterior Lighting | C of C |  | 2019-03-22 | 1 | OD
CAPITAL CAMPUS 0985-000
Conoy House | 00-06822.00 | 201990286 | 0985-043 | Roof Replacement | C of C |  | 2019-04-11 | 1 | OD
CUB | 00-06590.00 |  | 0985-011 | Mechanical Room Roof Replacement | Rejected | 2019-03-29 | 2019-04-11 | 1 | OD
CUB | 00-06590.00 | 201990431 | 0985-011 | Mechanical Room Roof Replacement | C of C | 2019-04-17 | 2019-05-01 | 1 | OD
CUB | 00-06590.00 | 201900537 | 0985-011 | Roof Fall Protection | C of O |  | 2019-05-28 | 2 | OD
Kettle House | 00-06822.00 | 201990285 | 0985-042 | Roof Replacement | Building Permit |  | 2019-04-11 | 1 | OD
Mahanoy House | 00-06822.00 | 201990284 | 0985-041 | Roof Replacement | Building Permit |  | 2019-04-11 | 1 | OD
Maintenance & Operations | 00-06706.00 | 201900399 | 0985-016 | Parking Office Addition | Building Permit |  | 2019-04-18 | 2 | OD
Muncy House | 00-06822.00 | 201990282 | 0985-036 | Roof Replacement | C of C |  | 2019-04-11 | 1 | OD
Nittany Village Bldg A | 00-06741.00 | 201900589 | 0985-110 | Waste Room Repurpose | Building Permit | 2019-04-25 | 2019-06-10 | 2 | OD
Nittany Village Bldg A | 00-06741.00 | 201900828 | 0985-110 | Generator Replacement | Building Permit | 2019-06-26 | 2019-08-06 | 2 | OD
Nittany Village Bldg A | 00-06741.00 |  | 0985-110 | Fire Alarm Upgrades | Pending | 2019-12-13 |  | 2 | OD | keister
Nittany Village Bldg B | 00-06741.00 | 201900590 | 0985-111 | Waste Room Repurpose | C of O | 2019-04-25 | 2019-06-10 | 2 | OD
Nittany Village Bldg B | 00-06741.00 | 201900829 | 0985-111 | Generator Replacement | Building Permit | 2019-06-26 | 2019-08-06 | 2 | OD
Nittany Village Bldg B | 00-06741.00 |  | 0985-111 | Fire Alarm Upgrades | Pending | 2019-12-13 |  | 2 | OD | keister
Nittany Village Bldg C | 00-06741.00 | 201900591 | 0985-112 | Waste Room Repurpose | Building Permit | 2019-04-25 | 2019-06-10 | 2 | OD
Nittany Village Bldg C | 00-06741.00 | 201900830 | 0985-112 | Generator Replacement | Building Permit | 2019-06-26 | 2019-08-06 | 2 | OD
Nittany Village Bldg C | 00-06741.00 |  | 0985-112 | Fire Alarm Upgrades | Pending | 2019-12-13 |  | 2 | OD | keister
Olmsted | 00-06850.00 | 201900523 | 0980-001 | Mail Room Reno | C of O | 2019-04-16 | 2019-05-23 | 2 | OD
Paxton House | 00-06822.00 |  | 0985-100 | Roof Replacement | Rejected |  | 2019-04-11 | 1 | OD
Sherman House | 00-05735.00 | 201900261 | 0985-040 | Mechanical Room Repairs | Building Permit | 2019-02-22 | 2019-03-15 | 2 | OD
Smart Home | 00-06483.00 |  | 0985-106 | Renovations | Rejection |  | 2019-03-01 | 2 | OD
Smart Home | 00-06483.00 | 201900322 | 0985-106 | Renovations - resubmission | Building Permit | 2019-03-12 | 2019-03-28 | 2 | OD
Soccer Fields | 00-06361.00 | 201901212 | 0985-000 | Synthetic Turf | Building Permit | 2019-10-10 | 2019-10-23 | 2 | OD
Village Community Ctr | 00-06822.00 | 201990281 | 0985-035 | Roof Replacement | C of C | 2019-03-29 | 2019-04-11 | 1 | OD
Wiconisco House | 00-06822.00 | 201990283 | 0985-039 | Roof Replacement | Building Permit |  | 2019-04-11 | 1 | OD
DICKINSON SCHOOL OF LAW-CARLISLE 0991-000
DUBOIS CAMPUS 0976-000
FAYETTE CAMPUS 0984-000
Athletic & Rec Center | 00-06651.00 | 201900521 | 0984-005 | Store Front and Door Replacement | Building Permit |  | 2019-05-23 | 2 | OD
Multiuse Pavilion | 00-06652.00 | 201900697 | 0984-006 | Demolition | C of C | 2019-06-03 | 2019-07-02 | demo | OD
Williams | 00-05654.00 | 201900452 | 0984-002 | Plaza Upgrades | C of O | 2019-04-02 | 2019-04-29 | 2 | OD
FRUIT RESEARCH CENTER 0968-000
FREC Pole Building | 00-06477.00 |  | 0968-000 | New Structure | Rejected | 2019-08-30 | 2019-10-09 | 2 | OD
Workshop/Storage Bldg | 00-06477.00 | 201901327 | 0968-023 | ADA Improvements | Building Permit | 2019-11-06 | 2019-12-09 | 2 | OD
GREAT VALLEY 0993-000
GREATER ALLEGHENY CAMPUS 0978-000
McKeesport Hall | 00-05534.00 | 201900912 | 0978-019 | Kitchen Fan Upgrade | C of O |  | 2019-08-22 | 2 | OD
HAZELTON CAMPUS 0973-000
Kostos | 00-01874.00 | 201990251 | 0973-009 | Window Flashing Repair | C of C | 2019-03-13 | 2019-03-28 | 1 | OD
Library | 00-06162.00 | 201900423 | 0973-006 | Knowledge Commons Renewal | Building Permit | 2019-03-18 | 2019-04-23 | 2 | OD
Library | 00-06162.00 | 201901178 | 0973-006 | Knowledge Commons Fire Alarm & Sprinkler | Building Permit | 2019-09-25 | 2019-10-17 | 2 | OD
South Hall | 00-06240.00 | 201900917 | 0973-011 | Kitchen Fan Upgrade | C of O |  | 2019-08-22 | 2 | OD
South Hall | 00-07012.00 | 201991868 | 0973-011 | Stabilize Exterior Masonry Wall | Building Permit |  | 2020-01-03 | 1 | OD
HERSHEY 0990-000
LEHIGH VALLEY 0977-000
Academic Bldg | 00-05264.00 | 201900433 | 0977-100 | Building Addition | Building Permit |  | 2019-04-29 | 2 | OD
Academic Bldg | 00-05264.00 | 201900435 | 0977-100 | Building Addition 1st Flr Fit-out | Building Permit |  | 2019-04-29 | 2 | OD
Academic Bldg | 00-05264.00 | 201900434 | 0977-100 | Building Addition 2nd Flr Fit-out | Building Permit |  | 2019-04-29 | 2 | OD
Academic Bldg | 00-05264.00 | 201900588 | 0977-100 | Bldg Addition - Land Development Revision | Building Permit |  | 2019-06-12 | 2 | OD
Academic Bldg | 00-06989.00 | 201900994 | 0977-100 | Office 139A Reno | C of O | 2019-08-05 | 2019-09-11 | 2 | OD
Maintenance Bldg | 00-06000.00 |  | 0977-200 | New Structure | Pending | 2019-09-06 |  | 2 | OD
MONT ALTO CAMPUS 0970-000
Millstream | 00-06815.00 | 201900683 | 0971-018 | Roof and HVAC Replacement | C of O | 2019-05-03 | 2019-06-26 | 2 | OD
Millstream | 00-06815.00 | 201900540 | 0971-018 | Roof Fall Protection | Building Permit |  | 2019-05-28 | 2 | OD
Mont Alto Hall | 00-06671.00 | 201900258 | 0971-011 | Exterior Lighting Upgrades | C of O | 2019-02-19 | 2019-03-15 | 2 | OD
Mont Alto Hall | 00-05578.00 | 201900914 | 0971-011 | Kitchen Fan Upgrade | C of O |  | 2019-08-22 | 2 | OD
Multipurpose Activities Center | 00-06452.00 | 201900244 | 0971-021 | Wrestling Mat Hoist | Building Permit |  | 2019-03-12 | 1 | OD
Multipurpose Activities Center | 00-06726.00 | 201990359 | 0971-021 | Roof covering Replacement | C of C |  | 2019-04-16 | 1 | OD
Multipurpose Activities Center | 00-06726.00 | 201900542 | 0971-021 | Roof Fall Protection | Building Permit |  | 2019-05-21 | 2 | OD
Wiestling Hall | 00-06670.00 | 201900385 | 0971-003 | First Floor Restroom Reno | C of O | 2019-03-22 | 2019-04-12 | 2 | OD
NAVY YARD
CBEEI Bldg 7R | 00-06127.00 | 201900539 | 0999-091 | Roof Fall Protection | Building Permit |  | 2019-05-28 | 2 | OD
CBEEI Bldg 7R | 00-06257.00 | 201900654 | 0999-091 | Lighting & Landscape Improvements | Building Permit |  | 2019-06-27 | 2 | OD
CBEEI Bldg 7R | 00-06171.00 | 201900993 | 0999-091 | Limited Façade and Roof Repairs | Building Permit | 2019-08-01 | 2019-09-13 | 2 | OD
Bldg 661 EE | 00-06257.00 | 201900653 | 0998-269 | Lighting & Landscape Improvements | Building Permit |  | 2019-06-27 | 2 | OD
Bldg 661 EE | 00-06171.00 | 201900991 | 0998-269 | Limited Façade and Roof Repairs | Building Permit | 2019-08-01 | 2019-09-13 | 2 | OD
NEW KENSINGTON 0981-000
Admin/Science | 00-00777.00 | 201900831 | 0981-001/5 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
Admin/Science | 00-00777.00 | 201900835 | 0981-001/5 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
Classroom/Gym | 00-00777.00 | 201900836 | 0981-006 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
Conference Center | 00-00777.00 | 201900839 | 0981-010 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
Engineering | 00-00777.00 | 201900832 | 0981-002 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
Science & Tech Ctr | 00-00777.00 | 201900838 | 0981-009 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD | Pete Caporusio
Student Union | 00-06684.00 | 201900529 | 0981-007 | Generator upgrade | Building Permit | 2019-04-16 | 2019-05-22 | 2 | DS
Student Union | 00-04209.00 | 201900541 | 0981-007 | Roof Fall Protection | Building Permit |  | 2019-05-28 | 2 | OD
Student Union | 00-00777.00 | 201900837 | 0981-007 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
Student Union | 00-04209.00 |  | 0981-007 | Roof Replacement | Pending | 2019-12-13 |  | 1 | OD
Theatre (Activity Ctr) | 00-06535.00 | 201801418 | 0981-004 | Theatre HVAC Replacement | Building Permit |  | 2019-01-03 | 2 | OD | Pete Caporusio
Theatre (Activity Ctr) | 00-06920.00 | 201900473 | 0981-004 | Main Distribution Panel Replacement | Building Permit | 2019-04-04 | 2019-05-13 | 2 | DS
Theatre (Activity Ctr) | 00-00777.00 | 201900833 | 0981-003/4 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
Theatre (Activity Ctr) | 00-00777.00 | 201900834 | 0981-003/4 | Fire Alarm Upgrades | Building Permit |  | 2019-08-05 | 2 | OD
WWTP | N/A |  | 0981-045 | Dichlorination Utility Shed | Rejected | 2019-03-19 | 2019-04-30 | 2 | OD
WWTP | 00-05395.00 | 201900632 | 0981-045 | Dichlorination Utility Shed Resubmission | C of O | 2019-05-02 | 2019-06-18 | 2 | OD
ROCK SPRINGS 0959-000
SCHUYLKILL CAMPUS 0975-000
Health & Wellness | N/A |  | 0975-001 | Ice Machine | Pending | 2019-12-12 |  | 1 | OD
Student Activities Center | 00-06572.00 | 201900228 | 0975-002 | Dining Terrace | C of O |  | 2019-03-12 | 2 | OD
SHAVERS CREEK 0960-000
SHENANGO CAMPUS
Sharon Hall | 00-06102.00 |  | 0987-002 | Courtyard ADA Lift | Pending | 2019-03-29 |  | 2 | OD
Sharon Hall | 00-06847.00 | 201900553 | 0987-002 | Roof Fall Protection | Building Permit | 2019-04-25 | 2019-05-28 | 2 | OD
Sharon Hall | 00-06847.00 | 201900639 | 0987-002 | Rooftop Unit Replacement | Building Permit | 2009-05-13 | 2019-06-20 | 2 | OD
WARMINSTER 0998-000
WILKES-BARRE CAMPUS 0983-000
WORTHINGTON-SCRANTON CAMPUS 0982-000
Dawson | 00-06704.00 | 201900466 | 0982-001 | First Floor Reno Revision | C of O | 2019-04-01 | 2019-05-07 | 2 | OD
Dawson | 00-06704.00 | 201900822 | 0982-001 | First Floor Reno - Sprinkler | C of O |  | 2019-08-07 | 2 | OD
Student Study Learning Ctr | 00-06675.00 | 201900687 | 0982-004 | Restroom Renovations | Building permit | 2019-05-31 | 2019-06-26 | 2 | OD
YORK CAMPUS 0964-000
Bradley Building | 00-06677.00 | 201990360 | 0964-012 | Roof Replacement | Building Permit | 2019-04-01 | 2019-04-18 | 1 | OD
Graham Center | 00-05982.00 | 201900465 | 0964-009 | New Structure | Building Permit |  | 2019-05-06 | 2 | OD
Main Bldg | 00-06676.00 | 201990361 | 0964-001 | Roof Replacement | C of C | 2019-04-01 | 2019-04-18 | 1 | OD
Main Bldg | 00-06676.00 | 201900543 | 0964-001 | Roof Fall Protection | C of O |  | 2019-05-21 | 2 | OD
Main Bldg | 00-05832.00 | 201901315 | 0964-001 | HVAC Reno | Building Permit | 2019-11-07 | 2019-12-03 | 2 | OD