## University Park
UNIVERSITY PARK CAMPUS 2021
BUILDING NAME | PSU Proj.# | Permit # | L&I File# | Bldg.# | Description | Status | Date Sent to L&I | Date Returned | Level of Permit | Design Services / Outside Designer
Academic Projects | 00-07371.00 | 202100071 | 541499 | 0407-000 | Lab 207 HVAC Reno | C of O | 2021-02-03 | 2021-04-16 | 2 | DS | Brian Hayes | B. Ondrasik, M. Rupert
Ag Science & Industries | 00-08167.00 | 202100244 | 541900 | 0116-000 | Rm 144 Electrical Reno | C of O | 2021-04-01 | 2021-09-15 | 2 | DS | Morgan VanOuse | Bob Z
Airport Aircraft Rescue & Firefighting | 00-05401.02 | 202100485 | 542528 | 0963-032 | New Structure - Sprinkler | Building Permit |  | 2021-06-15 | 2 | OD | Kurt coduti |  | Mike Kulbacki
Airport Aircraft Rescue & Firefighting | 00-05401.02 |  |  | 0963-032 | New Structure - Fire Alarm | Pending | 2021-07-13 |  | 2 | OD | Kurt coduti
Airport Aircraft Rescue & Firefighting | 00-05401.02 |  |  | 0963-032 | New Structure - Signage | PEnding | 2021-07-13 |  | 2 | OD | Kurt coduti
Animal Diagnostic Lab | 00-08302.00 | 202100416 | 542405 | 0169-002 | Room B002A & 31 HVAC Install | Building Permit | 2021-04-05 | 2021-05-10 | 2 | DS | Bart Monahan | Adam Davis
Animal Diagnostic Lab | 00-08113.00 | 202101168 | 543979 | 0169-002 | Labs 8, 10 & 11 and Exterior Ramp Upgrades | Building Permit | 2021-10-13 | 2021-11-29 | 2 | DS | Morgan VanOuse | Forrest Rishel
Animal, Vet & Biomed (New Henning) | 00-05321.00 | 202100395 | 542260 | 0119-000 | New Structure - Fire Alarm | C of O | 2021-04-28 | 2021-11-08 | 2 | OD | Jeff Spackman
Analytical Services Lab (Soils Lab) | 00-06838.00 | 202100966 | 543213 | 0180-004 | Labs 102, 109, 111, 116, 122, 124 & 131 New Casework | Building Permit | 2021-08-20 | 2021-10-07 | 2 | OD | Morgan VanOuse
ARL West 1 | 00-07538.00 | 202100280 | 542073 | 0996-019 | Helium Recovery System | C of O | 2021-04-03 | 2021-11-18 | 2 | OD | Bill Waugh
ARL West 3 | 00-06728.00 | 202100342 | 542160 | 0066-000 | Office Reno | C of O | 2021-04-18 | 2021-11-23 | 2 | OD | Bill Waugh
ARL West 3 | 00-06728.03 | 202100833 | 543013 | 0066-000 | Office Reno - Sprinkler | C of O | 2021-09-14 | 2021-11-23 | 2 | OD | Bill Waugh
Beaver Stadium | 00-04533.00 | 202100719 | 542800 | 0812-000 | Gate E Improvements | C of O | 2021-08-03 | 2021-09-04 | 2 | OD | Terry Hansel
Beaver Stadium | 00-04533.00 | 202190670 | 542807 | 0812-000 | Ribbon Board Replacement | C of C | 2021-08-11 | 2021-09-04 | 1 | DS/OD | Terry Hansel | Rupert, Royce Wall
Beaver Stadium | 00-04533.00 | 202190723 | 542931 | 0812-000 | Chiller Replacement | Building Permit | 2021-07-01 | 2021-09-07 | 1 | DS/OD | Terry Hansel | Rupert, Jamie Merrill
Beaver Stadium | 00-04533.00 | 202190731 | 543044 | 0812-000 | Evac Sound System Upgrades | C of C | 2021-09-16 | 2021-10-01 | 1 | DS/OD | Terry Hansel | Rupert, Pete Brumberg
Beaver Stadium | 00-04533.00 | 202100853 | 543030 | 0812-000 | Column Repair | Building Permit | 2021-07-28 | 2021-09-07 | 2 | OD | Terry Hansel
Beaver Stadium | 00-04533.00 | 202190844 | 543159 | 0812-000 | Fire Suppression Piping Replacement | Building Permit | 2021-08-09 | 2021-09-16 | 1 | DS | Mike Rupert
Bigler Hall | 00-06750.00 | 202100838 | 543041 | 0249-000 | Phase 2B Reno - Code Revision | Building Permit |  | 2021-09-14 | 2 | OD | Rich O'Donald
Biglar Hall | 00-06750.00 | 202101281 | 544477 | 0249-000 | Phase 2B Reno - Rebid and Plan Revision | Building Permit |  | 2021-09-14 | 2 | OD | Rich O'Donald
Biobehavioral Health | 00-08147.00 | 202100521 | 542465 | 0654-000 | Reno Rms 3 & 130 to add Office Space | Building Permit | 2021-04-23 | 2021-06-15 | 2 | DS | Robert Ligenfelter | Andy Bucha
Bluford (230 bldg) | 00-08129.00 | 202101111 | 544100 | 0965-002 | Mechanical Room M174 Reno | Building Permit | 2021-10-21 | 2021-11-18 | 2 | DS | Alan Zimmerman | Ting Zhou
Boucke | 00-07497.00 | 202101042 | 543193 | 0013-000 | Single User Toilet | Building Permit | 2021-09-23 | 2021-11-02 | 2 | DS | Ron Perttu | Scot M.
Boucke | 00-08221.00 |  |  | 0013-000 | Classroom 304 Renovation | Rejected | 2021-09-07 | 2021-10-20 | 2 | DS | Matt Leah | Debbie Fuller
Boucke | 00-08221.00 | 202101203 | 543455 | 0013-000 | Classroom 304 Renovation - Resubmission | Building Permit | 2021-11-10 | 2021-12-07 | 2 | DS | Matt Leah | Debbie Fuller
Breazeale Nuclear Reactor | 00-06441.00 | 202100404 | 542072 | 0325-000 | Neutron Beam Lab Addition | Building Permit | 2021-03-09 | 2021-05-03 | 2 | OD | Dwayne Rush
Breazeale Nuclear Reactor | 00-06441.00 | 202101194 | 544463 | 0325-000 | Neutron Beam Lab Addition - Sprinkler | Building Permit |  | 2021-12-10 | 2 | OD | Dwayne Rush |  | Steve Merrick
Bryce Jordan Ctr | 00-07391.00 | 202100461 | 542440 | 0045-000 | Stand 300 Kitchen Hood Install | C of O | 2021-05-26 | 2021-08-25 | 2 | OD | Nate Patrick
Bryce Jordan Ctr | N/A | 202190510 | 542464 | 0045-000 | Install of ShotTracker Sensors | Building Permit | 2021-04-27 | 2021-06-04 | 1 | DS |  | Mike Rupert
Bryce Jordan Ctr | 00-06501.00 |  |  | 0045-000 | Basketball Suite Reno Ph2 - Fire Alarm | Rejected |  | 2021-09-07 | 2 | OD | Marv Bevan
Bryce Jordan Ctr | 00-06501.00 | 202101300 | 543170 | 0045-000 | Basketball Suite Reno Ph2 - Fire Alarm | C of O | 2022-01-11 | 2022-01-25 | 2 | OD | Marv Bevan
Bryce Jordan Ctr | 00-06501.00 | 202100951 | 543402 | 0045-000 | Basketball Suite Reno Ph2 - Sprinkler | C of O | 2021-10-13 | 2021-10-19 | 1 | OD | Marv Bevan
Bryce Jordan Ctr | 00-08270.00 | 202100950 | 543401 | 0045-000 | Telecom Rooms HVAC Upgrade | Building Permit |  | 2021-10-05 | 2 | OD | Nate Patrick
Business Bldg | 00-07295.00 | 202100111 | 541435 | 0023-001 | Fire Retardant Coating Repair | Building Permit |  | 2021-02-15 | 2 | OD | Robert Ligenfelter
Carnegie | 00-07098.00 | 202100188 | 541752 | 0704-000 | Ground Floor Reno | C of O | 2021-01-25 | 2022-03-04 | 2 | OD | Matt Leah
Carnegie | 00-07098.00 | 202100806 | 542878 | 0704-000 | Ground Floor Reno - Sprinkler | C of O | 2021-08-30 | 2022-03-04 | 2 | OD | Matt Leah
Carnegie | 00-07098.00 | 202100467 | 542367 | 0704-000 | Second Floor Reno - Dean & Advising Suite Reno | C of O | 2021-04-09 | 2022-03-11 | 2 | OD | Matt Leah
Carnegie | 00-07098.00 | 202101050 | 543582 | 0704-000 | Second Floor Reno - Sprinkler | C of O | 2021-11-02 | 2022-03-11 | 2 | OD | Matt Leah
Chandlee Lab | 00-08400.00 | 202101158 | 544020 | 0408-000 | 14T Electrical Upgrades | C of O | 2021-10-21 | 2022-03-10 | 2 | OD | Jason Smith
Chemical & Biomedical Engineering | 00-08306.00 |  |  | 0405-002 | Lab 223 Gas Cabinet | Rejected | 2021-06-15 | 2021-08-11 | 1 | OD/DS | Dwayne Rush | Mike Rupert
Chemical & Biomedical Engineering | 00-08306.00 | 202101110 | 544096 | 0405-002 | Lab 223 Gas Cylinder Cabinet | Building Permit | 2021-10-21 | 2021-11-16 | 2 | OD | Dwayne Rush
Chemistry | 00-07166.00 | 202100101 | 541413 | 0050-000 | Helium Pipe Install | C of O | 2020-12-21 | 2021-02-09 | 2 | DS | Matt Leah | Bryan O, Pete C.
Chemistry | 00-08014.00 | 202100460 | 541896 | 0050-000 | Lab 304 Cold Room | C of O | 2021-05-21 | 2021-07-16 | 2 | DS | Jason Anderson | Pete Caporuscio
Curtin Hall | 00-06750.00 | 202100837 | 543042 | 0248-000 | Phase 2B Reno - Code Revision | Building Permit |  | 2021-09-14 | 2 | OD | Rich O'Donald
Curtin Hall | 00-06750.00 | 202101206 | 544476 | 0248-000 | Phase 2B Reno - Plan Revision | Building Permit |  | 2021-12-10 | 2 | OD | Rich O'Donald
Dairy Barn B | 00-06386.00 | 202100801 | 542936 | 0168-002 | Demolition of Structure | C of O | 2021-09-07 | 2021-09-15 | demo | DS | Jeff Spackman | Forrest, Reasinger
Dairy Barn C | 00-06386.00 | 202100800 | 542937 | 0168-002 | Demolition of Structure | C of O | 2021-09-07 | 2021-09-15 | demo | DS | Jeff Spackman | Forrest, Reasinger
Davey Lab | 00-07524.00 | 202190314 | 541880 | 0412-000 | Astrology Dome | C of C | 2021-03-18 | 2021-07-16 | 1 | OD | Jason Anderson
Davey Lab | 00-08246.00 | 202100577 | 542577 | 0412-000 | Lab 21 Renovation | C of O | 2021-05-10 | 2022-01-03 | 2 | OD | Jason Anderson
Earth & Engineering Science | 00-08128.00 | 202100117 | 541612 | 0035-000 | Rm 3A Exhaust Fan Install | Building Permit | 2021-01-19 | 2021-02-24 | 2 | DS | Robert Ligenfelter | Adam Davis
Earth & Engineering Science | 00-06866.00 | 202101208 | 544387 | 0035-000 | Demolition and Entrance Renovation | Building Permit |  | 2021-12-10 | 2 | OD | Dwayne Rush
East Halls Pump Station | 00-07019.00 | 202100104 | 541606 | 0914-001 | Pump Station Upgrades | Building Permit | 2021-01-13 | 2021-02-11 | 2 | OD | Dave Peck
Eisenhower Auditorium | 00-06584.00 | 202100010 | 541402 | 0011-000 | Shaft Wall Second Revision | Building Permit |  | 2021-01-12 | 2 | OD | Robert Ligenfelter
Electrical Engineering East | 00-07353.00 | 202100072 | 541414 | 0315-000 | RM 16 ALD Equipment Upgrades | C of O | 2020-12-21 | 2021-08-05 | 2 | DS | Dwayne Rush | Bryan Ondrasik
Electrical Engineering West | 00-08166.00 | 202100246 | 541948 | 0302-000 | Suite 207 add new office | C of O | 2021-03-24 | 2021-08-25 | 2 | OD | Dwayne Rush
Electrical Engineering West | 00-07296.00 | 202100475 | 542460 | 0302-000 | Room 6 Reno - Fire Alarm | C of O | 2021-06-08 | 2021-09-02 | 2 | OD | Bryan Hayes
Electrical Engineering West | 00-08213.00 | 202101141 | 544025 | 0302-000 | Ph 2 Process Chiller Replacement | Building Permit | 2021-10-19 | 2021-11-29 | 2 | DS | Alan Zimmerman | Ting Zhou
Elliot Bldg (James) | 00-07109.00 | 202190311 | 541879 | 0034-001 | Roof Replacement | Building Permit | 2021-02-09 | 2021-03-18 | 1 | DS | Christie Holloway | Dan Aumiller
Elliot Bldg (James) | 00-07109.00 | 202100360 | 541971 | 0034-001 | Roof and HVAC Equipment Renewal | Building Permit | 2021-02-25 | 2021-04-20 | 2 | OD | Christie Holloway |  | Ben Bidelspach
Fed EX | 00-06235.00 |  |  | 0963-018 | Upgrades for Occ - Men's room 104 & new shower 104A | Pending | 2021-12-10 |  | 2 | DS | Matt Vail | Forrest, Evan C and Bob Z.
Fed EX | 00-06235.00 |  |  | 0963-018 | Upgrades for Occ - Women's room 105, kitchenette & exterior | Pending | 2021-12-10 |  | 2 | DS | Matt Vail | Forrest, Evan C and Bob Z.
Forum | 00-08163.00 | 202100561 | 542522 | 0753-000 | Classroom 102 Reno | C of O | 2021-05-03 | 2022-03-11 | 2 | DS | Matt Leah | Deb, Bob Z., Bryan O.
Forum | 00-08163.00 | 202100508 | 542524 | 0753-000 | Classroom 108 Reno | C of O | 2021-05-03 | 2022-03-11 | 2 | DS | Matt Leah | Deb, Bob Z., Bryan O.
Forum Modular Lab | 00-06902.01 | 202101095 | 543980 | 0970-072/0753-000 | Modular Lab relocated to University Park - Foundation | Building Permit | 2021-10-13 | 2021-11-12 | 2 | DS | Jeff Spackman | Dave R., Ryan D, Forrest
Forum Modular Lab | 00-06902.02 | 202101212 | 544237 | 0970-072/0753-000 | Modular Lab relocated to University Park Ph 2 - Trailer | Building Permit | 2021-11-02 | 2021-12-10 | 2 | DS | Jeff Spackman | Dave R., Ryan D, Forrest
Fox Hollow Bldg | 00-06950.00 | 202100008 | 541108 | 0193-005 | Carpenter & Paint Shop Relocation Electrical Revision | Building Permit | 2020-11-16 | 2021-01-07 | 2 | DS | Ron Perttu | Pete Caporuscio
General Aviation Hanger III | 00-08195.00 | 202101093 | 543870 | 0963-019 | Airport COE Wind Tunnel | Building Permit | 2021-10-11 | 2021-11-10 | 2 | OD | Bryan Hayes
Hallowell | 00-08381.00 | 202101295 | 544630 | 0317-000 | Lab B008 ME and Elec Revisions | Building Permit | 2021-12-08 | 2022-01-04 | 2 | OD | Alan Zimmerman
Hammond | 00-08000.00 | 202100154 | 541611 | 0304-000 | Lab 42D Reno | Building Permit | 2021-01-19 | 2021-03-05 | 2 | DS | Julie Patrick | Andy Bucha
Headhouse 3 | 00-08491.00 | 202101107 | 543929 | 0160-000 | 131 Sprinkler Replacement | Building Permit | 2021-10-13 | 2021-11-16 | 2 | OD | Heath Lorson
Health & Human Development | 00-07499.00 | 202100616 | 542661 | 0652-000 | Room 432 Reconfiguration | C of O | 2021-05-28 | 2022-02-01 | 2 | OD | Robert Ligenfelter
Henning Replacement Bldg | 00-05321.00 | 202100192 | 541890 | 0119-000 | New Structure - Sprinkler | C of O | 2021-05-10 | 2021-11-03 | 2 | OD | Jeff Spackman
Henning Replacement Bldg | 00-05321.00 | 202100395 | 542260 | 0119-000 | New Structure - Fire Alarm | C of O | 2021-05-10 | 2021-11-03 | 2 | OD | Jeff Spackman
HUB Parking Deck | 00-07475.00 | 202190368 | 541753 | 0995-080 | Structure and Façade Rehab | C of C | 2021-01-25 | 2022-01-03 | 1 | DS/OD | Tyler Payne,Kurt Coduti
HUB | 00-07253.00 | 202100470 | 542451 | 0005-000 | Slim Chicken Fit-out | C of O | 2021-06-08 | 2021-08-25 | 2 | OD | Matt Vail
Innovation Hub(James Bldg Replacement) | 00-06403.00 | 202101251 | 544514 | 0054-000 | Fit-Out L3 & L6 | Building Permit | 2021-11-29 | 2022-01-03 | 2 | OD | David Peck
Intramural Bldg | 00-07433.00 | 202100402 | 542268 | 0804-000 | Rooms 127 & 129 Reno | Building Permit | 2021-03-30 | 2021-05-03 | 2 | DS | Derek Leonard | Kathy P, Bryan O, Scott M.
Johnston Commons | 00-08316.00 | 202100752 | 542786 | 0276-000 | UP-C Store Distribution Center Reno | Building Permit | 2021-06-16 | 2021-08-13 | 2 | OD | Matt Vail
Johnston Commons | 00-06750.00 | 202101135 | 544101 | 0276-000 | Building Reno - Code Revision | Building Permit |  | 2021-11-23 | 2 | OD | Rich O'Donald
Kern | 00-03448.00 | 202100573 | 542598 | 0452-000 | Lobby Reno | Building Permit | 2021-05-18 | 2021-06-29 | 2 | OD | Jason Smith
Lasch | 00-06019.00 | 202100052 | 541150 | 0845-000 | Quarter Back Positions Room - Sprinkler Drawings only | Building Permit |  | 2021-01-12 | 2 | OD | Marv Bevan
Lasch | 00-06882.00 | 202100084 | 541408 | 0845-000 | Building Reno and Addition | Building Permit |  | 2021-02-03 | 2 | OD | Marv Bevan
Lasch | 00-06882.00 | 202100900 | 543165 | 0845-000 | Building Reno and Addition - Fire Alarm | Building Permit |  | 2021-09-23 | 2 | OD | Marv Bevan
Lasch | N/A | 202190424 | 542215 | 0845-000 | New circuit for Cyrotherm Units in East Area Locker rm | Building Permit | 2021-03-29 | 2021-04-28 | 1 | DS | Marv Bevan | Mike Rupert
McKee Hall | 00-08238.00 | 202101142 | 544214 | 0206-000 | Exterior Stair Renovation | Building Permit | 2021-10-28 | 2021-11-29 | 2 | OD | Matt Vail
Millennium Science | 00-06289.00 | 202100934 | 543297 | 0038-001 | W-244B Alterations | Building Permit | 2021-08-24 | 2021-09-30 | 2 | OD | Jason Smith
Millennium Science | 00-08428.00 | 202100959 | 543412 | 0038-001 | Cleanroom Equipment N-109M Power UPgrades | Building Permit | 2021-08-31 | 2021-10-07 | 2 | OD | Jason Smith
Millennium Science | 00-08437.00 | 202101084 | 544016 | 0038-001 | E-Beam Power in Cleanroom | Building Permit | 2021-10-18 | 2021-11-10 | 2 | OD | Jason Smith |  | Ben Bidelspach
Mueller | 00-08597.00 | 202200021 | 544653 | 0409-000 | Rooms 514 & 606 Reno | Building Permit | 2021-12-10 | 2022-01-13 | 2 | OD | Jason Anderson
North Campus Chiller Plant | 00-06044.00 | 202100579 | 542580 | 0910-004 | Fire Pump Room Modifications - Fire Alarm | Building Permit | 2021-05-12 | 2021-07-13 | 2 | DS | Nate Patrick, Jeff Lucas
Old Main | 00-08235.00 | 202100875 | 543009 | 0001-000 | Rm 417 Renovations | Building Permit | 2021-07-19 | 2021-09-13 | 2 | OD | Robert Ligenfelter
OPP | 00-07489.00 | 202100323 | 541991 | 0904-000 | Rooms 101Q, 102, 103 & 105 | Building Permit | 2021-03-02 | 2021-04-20 | 2 | DS | Ron Perttu | Forrest Rishel
OPP | 00-07489.00 | 202100324 | 542034 | 0904-000 | Rooms 202, 213 & 214 | C of O | 2021-04-20 | 2021-10-29 | 2 | DS | Ron Perttu | Forrest Rishel
OPP | 00-07489.00 | 202100575 | 542612 | 0904-000 | Second Floor and Mechanical Room 215 Reno | C of O | 2021-05-19 | 2022-01-03 | 2 | DS | Ron Perttu | Forrest, Bryan O, Bob Z
OPP | 00-07489.00 | 202100855 | 543038 | 0904-000 | 102, 103, Second Floor & ME Rm 215 - Sprinkler | C of O | 2021-07-19 | 2022-01-03 | 2 | DS | Ron Perttu | Forrest Rishel
Osmond Lab | 00-06021.00 | 202100199 | 541754 | 0401-000 | Radon Migitation | Building Permit | 2021-01-25 | 2021-03-18 | 2 | DS | Jason Anderson | Evan, Bryan O. Bob Z.
Packer Hall | 00-06750.00 | 202100839 | 543043 | 0247-000 | Phase 2B Reno - Code Revision | Building Permit |  | 2021-09-14 | 2 | OD | Rich O'Donald
Packer Hall | 00-06750.00 | 202101197 | 544475 | 0247-000 | Phase 2B Reno - Plan Revision | Building Permit |  | 2021-12-07 | 2 | OD | Rich O'Donald
Palmer Museum | 00-06767.00 | 202100665 | 542588 | 0758-000 | New Structure & Sprinkler | Building Permit | 2021-05-13 | 2021-07-23 | 2 | OD | Monica Reed
Pell Lab | 00-08058.00 | 202100226 | 541970 | 0169-020 | Kitchenette Relocation | Building Permit | 2021-02-23 | 2021-03-24 | 2 | DS | Morgan VanOuse | Forrest R., Debbie F.
Pell Lab | 00-05032.01 | 202100802 | 542865 | 0169-020 | Boiler Room Conditioning | Building Permit | 2021-06-29 | 2021-08-30 | 2 | OD | Morgan VanOuse
Pell Lab | 00-08237.00 | 202100965 | 543196 | 0169-020 | Room 119 Dehumidification | Building Permit | 2021-08-13 | 2021-10-04 | 2 | DS | Morgan Vanouse | Adam Davis
Pond Lab | 00-07139.00 | 202100076 | 541404 | 0403-000 | Steam to Hot Water Conversion Ph 2 | Building Permit | 2020-12-15 | 2021-02-03 | 2 | DS | Derek Leonard | Ting Zhou
Procurement Services | 00-08395.00 | 202190721 | 542938 | 0037-000 | Rm 113 Install Door and Frame | C of O | 2021-09-14 | 2021-09-21 | 1 | DS | Mike O'Brien
Reber | 00-07180.00 | 202100175 | 541878 | 0303-000 | Lab 108 & 109 Reno - Rev | C of O | 2021-03-18 | 2021-04-27 | 2 | DS | Julie Patrick | Forrest R. Bryan O.
Reasearch Bldg West | 00-07505.00 | 202100551 | 542570 | 0271-000 | ARL First floor HVAC Upgrades - Sprinkler | Building Permit | 2021-05-27 | 2021-06-24 | 2 | OD | Bill Waugh
Ritenour | 00-05724.00 | 202101162 | 544223 | 0051-000 | Millennium Scholars | Building Permit | 2021-10-28 | 2021-11-29 | 2 | OD | Ron Perttu
Sackett | 00-08480.00 | 202101188 | 544431 | 0301-000 | Accessibility Upgrades | Building Permit | 2021-11-11 | 2021-12-02 | 2 | DS | Ron Perttu | Andy Bucha
Salvage & Surplus Workshop | 00-08282.00 | 202100817 | 542874 | 0037-002 | Lion's Pantry Reno | Building Permit | 2021-06-29 | 2021-09-07 | 2 | DS | Derek Leonard | Andy Bucha
Shields | 00-06802.00 | 202100721 | 542744 | 0004-000 | 1ST Floor Partial Occupancy Areas A | C of O | 2021-06-08 | 2021-08-11 | 2 | OD | Chad Spackman
Shields | 00-06802.00 | 202100722 | 542745 | 0004-000 | 1ST Floor Partial Occupancy Areas B | C of O | 2021-06-08 | 2021-08-11 | 2 | OD | Chad Spackman
Shields | 00-06802.00 | 202100723 | 542746 | 0004-000 | 1ST Floor Partial Occupancy Areas C | C of O | 2021-06-08 | 2021-08-11 | 2 | OD | Chad Spackman
Shields | 00-06802.00 | 202100724 | 542747 | 0004-000 | 1ST Floor Partial Occupancy Areas D | C of O | 2021-06-08 | 2021-08-11 | 2 | OD | Chad Spackman
Shields | 00-06802.00 | 202100725 | 542748 | 0004-000 | 1ST Floor Partial Occupancy Areas E | C of O | 2021-08-11 | 2021-11-08 | 2 | OD | Chad Spackman
Shields | 00-06802.00 | 202100726 | 542749 | 0004-000 | 1ST Floor Partial Occupancy Areas F | C of O | 2021-06-08 | 2021-08-11 | 2 | OD | Chad Spackman
Sparks | 00-07285.00 | 202100426 | 542412 | 0701-000 | Suite 15 Reno | C of O | 2021-05-18 | 2021-10-19 | 2 | DS | Derek Leonard | Andy Bucha
Steidle | 00-08162.00 | 202100473 | 542447 | 0501-000 | Lab 318 Nitrogen Generator | C of O | 2021-04-20 | 2021-08-06 | 2 | DS | Dwayne Rush | Evan Cleary
Swine Research | 00-08112.00 | 202100612 | 542601 | 0132-000 | Replace Heating & Ventilation Units | Building Permit | 2021-05-18 | 2021-07-13 | 2 | DS | Morgan VanOuse | Bryan O. Jenks
Tennis Court Bldg | 00-07435.00 | 202100751 | 542826 | 0837-000 | Rms 101-104 Renovations | Building Permit | 2021-06-24 | 2021-08-10 | 2 | DS | Derek Leonard | Debbie Fuller
University Support Bldg 1 | 00-06806.00 | 202100843 | 542887 | 0193-002 | US and PS Dispatch and Emergency Management Ctr | Cancelled |  | 2021-09-14 | 2 | OD | Chad Spackman
University Support Bldg 1 | 00-06806.00 | 202101113 | 544121 | 0193-002 | US and PS Dispatch and Emergency Management Ctr | Building Permit |  | 2021-11-18 | 2 | OD | Chad Spackman
Wagner | 00-05183.00 | 202100990 | 543868 | 0014-000 | Indoor Rifle Range - Fire Alarm | C of O | 2021-10-25 | 2022-01-03 | 2 | OD | Ron Perttu
Wagner | 00-05183.00 | 202101114 | 544324 | 0014-000 | Indoor Rifle Range - Fire Alarm Rev | Building Permit | 2021-11-17 | 2022-01-03 | 2 | OD | Ron Perttu |  | Tom Lang
Walker Clubhouse | 00-06367.00 | 202100958 | 942948 | 0841-003 | 19th Hole Renovation | Building Permit |  | 2021-10-07 | 2 | OD | Marv Bevan
Warnock Hall | 00-06053.00 | 202100702 | 542726 | 0274-000 | Basement Partition Improvements | C of O | 2021-06-11 | 2022-02-15 | 2 | OD | Matt Vail
Weaver | 00-08455.00 | 202101024 | 543357 | 0109-000 | Rm 103C & R106 Single User Toilets | C of O | 2021-08-26 | 2022-02-15 | 2 | DS | Derek Leonard | Andy B, Pete C.
West 1 - Eng Research & Teaching | 00-06866.00 | 202100183 | 541546 | 0310-000 | New Structure | Building Permit | 2021-02-25 | 2021-03-11 | 2 | OD | Dwayne Rush
West Campus Chiller Building | 00-08097.00 | 202101086 | 543722 | 0943-000 | Refrigerant Storage Rooms 106 & 107 Modifications | Building Permit | 2021-09-30 | 2021-11-10 | 2 | DS | Nate Patrick | Ting Z, Bryan O.
West Campus Chiller Building | 00-06919.00 | 202101120 | 544209 | 0943-000 | 3000 Ton Expansion - Rm 117 Sprinkler (drawings only) | Building Permit |  |  | 2 | OD
West Campus Parking Deck | 00-05940.00 | 202100215 | 542071 | 0995-086 | New Structure - Fire Alarm | C of O | 2021-03-18 | 2021-04-27 | 2 | OD | Kurt Coduti
West Campus Power Plant | 00-04966.00 | 202100471 | 542435 | 0911-000 | Roof Upgrades | C of O | 2021-06-08 | 2021-11-18 | 2 | OD | Nate Patrick
Westgate | 00-07303.00 | 202100129 | 541494 | 0039-000 | 1St Floor CSE Office Reno | C of O | 2021-01-11 | 2021-08-06 | 2 | OD | Dwayne Rush
White | 00-06619.00 | 202100674 | 542625 | 0802-000 | eSports Gaming Room | Building Permit |  | 2021-07-23 | 2 | OD | Rich Odonald | Derek Leonard
Willard | 00-05743.00 | 202100231 | 541960 | 0012-000 | Foundation to Grade Reno - Partial Occupancy | C of O | 2021-03-24 | 2021-04-16 | 2 | OD | Monica Reed

## Commonwealth
CAMPUS 2021 | PSU PROJECT # | Permit # |  | BLDG. # | DESCRIPTION | STATUS | DATE SENT | DATE RETURNED | PERMIT LEVEL | DS/OD
ABINGTON CAMPUS 0979-000
ALTOONA CAMPUS 0974-000
Holtzinger Engineering | 00-07238.00 | 202100613 | 542599 | 0974-018 | Lab 208 & 209 Reno | Building Permit | 2021-05-19 | 2021-07-13 | 2 | OD | Doug Wenger
Housing and Food Service |  | 202191605 | 544580 | 0974-007 | Port Sky Ansul System Upgrades - All Fired Up | Building Permit | 2021-11-29 | 2022-01-05 | 1 | DS | Justin Keister
Housing and Food Service |  | 202191607 | 544583 | 0974-007 | Port Sky Ansul System Upgrades - Main Kitchen | Building Permit | 2021-11-29 | 2022-01-05 | 1 | DS | Justin Keister
Housing and Food Service |  | 202191606 | 544582 | 0974-007 | Port Sky Ansul System Upgrades - Flipping | Building Permit | 2021-11-29 | 2022-01-05 | 1 | DS | Justin Keister
Housing and Food Service |  | 202191608 | 544584 | 0974-007 | Port Sky Ansul System Upgrades - On A Roll | Building Permit | 2021-11-29 | 2022-01-05 | 1 | DS | Justin Keister
Housing and Food Service |  | 202191609 | 544585 | 0974-007 | Port Sky Ansul System Upgrades - Sunrise Sunset | Building Permit | 2021-11-29 | 2022-01-05 | 1 | DS | Justin Keister
Misciagna Theatre | 00-08172.00 | 202190508 | 542415 | 0974-001 | Lighting Replacement | Building Permit | 2021-04-14 | 2021-06-02 | 1 | OD | Doug Wenger
Smith | 00-08337.00 | 202100760 | 542809 | 0974-015 | E101 Office Reno | Building Permit | 2021-06-22 | 2021-08-13 | 2 | OD | Doug Wenger
BEAVER CAMPUS 0986-000
Food services | 00-05386.00 | 202100686 | 542592 | 0986-008 | Building Stabilization | Building Permit |  | 2021-07-28 | 2 | OD | Kyle Hollick
Laboratory Classroom | 00-07355.00 | 202100459 | 542445 | 0986-012 | Fire Alarm System Upgrades | C of O | 2021-05-26 | 2021-07-16 | 2 | OD | Justin Keister
Laboratory Classroom | 00-08292.00 | 202100942 | 543403 | 0986-012 | Boiler Replacement | Building Permit |  | 2021-09-30 | 2 | OD | Ron Kobelenski
Library | 00-08062.00 | 202100251 | 541891 | 0986-005 | Psychology Rooms | Building Permit |  | 2021-03-24 | 2 | OD | Ron Kobelenski
Police Services | 00-08120.00 | 202100710 | 542740 | 0986-011 | P&PS Building Reno | Building Permit |  | 2021-07-28 | 2 | OD | Marcus Marasco
BEHREND CAMPUS 0972-000
Carriage House | 00-07356.00 | 202100769 | 542710 | 0972-003 | Office Reno | Building Permit |  | 2021-08-20 | 2 | OD
Fasenmyer | 00-07042.00 | 202100066 | 541449 | 0972-080 | Swing Space - Sprinkler | Building Permit |  | 2021-02-03 | 2 | OD | Marcus Marasco
Federal House | 00-07049.00 | 202101253 | 544579 | 0972-071 | Building Reno and Addition - Sprinkler | Building Permit |  | 2022-01-03 | 2 | OD | Marcus Marasco
Junker Center | 00-08341.00 | 202100911 | 543194 | 0972-012 | Pool and Lobby Lighting Upgrades | BP/Cancelled |  | 2021-09-28 | 2 | OD | James Hoover
Niagara Hall | 00-08100.00 | 202190392 | 542090 | 0972-014 | Brick Masonry Re-pointing | C of C | 2021-03-08 | 2021-08-05 | 1 | OD | Justin Keister, Neal McNutt
Otto Behrend Science Bldg | 00-08319.00 | 202100969 | 543212 | 0972-011 | Gear Room AC | Building Permit |  | 2021-10-13 | 2 | OD | James Hoover
Perry Hall | 00-08340.00 | 202100778 | 542873 | 0972-013 | Lobby Power and Cooling Upgrades | C of O | 2021-08-20 | 2021-12-13 | 2 | OD | Justin Keister
Perry Hall | 00-08340.00 | 202101049 | 544103 | 0972-013 | Lobby Power and Cooling Upgrades Revision | C of O | 2021-11-02 | 2021-12-13 | 2 | OD | Justin Keister
Advanced Manufacturing & Innovation Ctr Bldg# 7 | N/A | 202100857 | 543157 | 0972-000 | Trucklite Fit-out - Lab Space | Building Permit |  | 2021-09-16 | 2 | OD | Dennis Wilkins WMF
Advanced Manufacturing & Innovation Ctr Bldg# 4 | N/A | 202100922 | 543218 | 0972-000 | Trucklite Fit-out - Office Space | Building Permit |  | 2021-09-28 | 2 | OD | Dennis Wilkins WMF
Advanced Manufacturing & Innovation Ctr Bldg# 4 | N/A | 202100865 | 543115 | 0972-000 | Vert Markets Fit-out | C of O |  | 2021-09-08 | 2 | OD | Chuck Peters
Advanced Manufacturing & Innovation Ctr Bldg# 4 | N/A | 202101199 | 544383 | 0972-000 | Vert Markets Fit-out - Sprinkler | C of O |  | 2021-12-14 | 2 | OD | Chuck Peters
BERKS CAMPUS 0980-000
Beaver Community Center | 00-06497.00 | 202100058 | 541459 | 0980-002 | Building Renovation Fire Alarm | C of O | 2021-01-25 | 2021-09-21 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100080 | 541456 | 0980-002 | Building Renovation Fire Alarm | Building Permit |  | 2\3\21 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100088 | 541458 | 0980-002 | Building Renovation Fire Alarm | Building Permit |  | 2\3\21 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100119 | 541858 | 0980-002 | Bldg Addition & Reno - Temporary Shower Demo | C of C | 2021-03-09 | 2021-03-11 | Demo | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100162 | 541730 | 0980-002 | Bldg Addition & Reno - Exterior Wall Revision | Building Permit |  | 2021-03-11 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100163 | 541728 | 0980-002 | Bldg Addition & Reno - Exterior Wall Revision | Building Permit |  | 2021-03-11 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100165 | 541731 | 0980-002 | Bldg Addition & Reno - Exterior Wall Revision | Building Permit |  | 2021-03-11 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100493 | 542473 | 0980-002 | Area A Partial Occupancy | C of O | 2021-06-08 | 2021-08-25 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100494 | 542474 | 0980-002 | Area B Partial Occupancy | C of O | 2021-06-08 | 2021-09-04 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100495 | 542475 | 0980-002 | Area C Partial Occupancy | C of O | 2021-06-08 | 2021-10-07 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100496 | 542476 | 0980-002 | Area D Partial Occupancy | Building Permit | 2021-05-08 | 2021-06-08 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100497 | 542477 | 0980-002 | Area E Partial Occupancy | C of O | 2021-06-08 | 2021-11-03 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100498 | 542478 | 0980-002 | Area F Partial Occupancy | C of O | 2021-06-08 | 2021-10-07 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100499 | 542479 | 0980-002 | Area G Partial Occupancy | C of O | 2021-06-08 | 2021-11-03 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100500 | 542480 | 0980-002 | Area H Partial Occupancy | C of O | 2021-06-08 | 2021-10-29 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202100501 | 542481 | 0980-002 | Area J Partial Occupancy | Building Permit | 2021-05-08 | 2021-06-08 | 2 | OD | kyle Hollick
Cedar Hall | 00-06863.00 | 202100217 | 541713 | 0980-066 | HVAC System Upgrade | C of O | 2021-03-18 | 2021-10-07 | 2 | OD | Neal McNutt
Greenbrier Hall | 00-06863.00 | 202100216 | 541714 | 0980-065 | HVAC System Upgrade | Building Permit |  | 2021-03-18 | 2 | OD | Neal McNutt
Food Services Bldg |  |  | 542592 |  |  | Rejection |  | 2021-06-29 |  | OD | Justin Keister
Perkins Student Ctr | 00-06497.00 | 202100079 | 541457 | 0980-005 | Building Renovation Fire Alarm | Building Permit |  | 2\3\21 | 2 | OD | kyle Hollick
Perkins Student Ctr | 00-06497.00 | 202100164 | 541729 | 0980-005 | Bldg Addition & Reno - Exterior Wall Revision | Building Permit |  | 2021-03-11 | 2 | OD | kyle Hollick
Perkins Student Ctr | 00-06497.00 | 202100491 | 542471 | 0980-005 | Area A Partial Occupancy | C of O | 2021-06-08 | 2021-09-04 | 2 | OD | kyle Hollick
Perkins Student Ctr | 00-06497.00 | 202100492 | 542472 | 0980-005 | Area B Partial Occupancy | C of O | 2021-06-08 | 2021-09-04 | 2 | OD | kyle Hollick
BRANDYWINE CAMPUS 0989-000
CAPITAL(Harrisburg) CAMPUS 0985-000
Boiler Plant | 00-07203.00 | 202100569 | 542496 | 0985-002 | Hot Water System Upgrades | Building Permit | 2021-04-29 | 2021-06-29 | 2 | OD | Doug Wenger
Conoy House | 00-07382.00 | 202190417 | 542107 | 0985-043 | Bathroom Reno | C of C |  | 2021-08-06 | 1 | OD | Neal McNutt
Kettle House | 00-07382.00 | 202190416 | 542108 | 0985-042 | Bathroom Reno | C of C |  | 2021-04-28 | 1 | OD | Neal McNutt
Mahanoy | 00-07382.00 | 202190542 | 542521 | 0985-042 | Bathroom Reno | C of C |  | 2021-08-06 | 1 | OD | Neal McNutt
Science & Technology Bldg | 00-07425.00 | 202100184 | 541798 | 0985-022 | Emergency Power Upgrades | C of O | 2021-03-18 | 2022-04-13 | 2 | OD
Susquehanna Bldg | 00-07323.00 | 202100302 | 542069 | 0985-010 | Police Services Reno - Mini Split System Rev | C of O | 2021-03-29 | 2021-08-25 | 2 | 2021-03-18 | Doug Wenger
DICKINSON SCHOOL OF LAW-CARLISLE 0991-000
Trickett Hall | 00-08121.00 | 202190827 | 543063 | 0991-001 | Portico Refurbishment | Building Permit |  | 2021-09-28 | 1 | OD | Andy Ritter
DUBOIS CAMPUS 0976-000
Multipurpose Bldg | 00-06709.00 | 202100828 | 542812 | 0976-007 | PAW Center Addition & Reno | Building Permit | 2021-06-18 | 2021-09-07 | 2 | OD | Doug Wenger
Smeal Bldg | 00-06709.00 | 202100850 | 542811 | 0976-001 | Building Renovations | C of O | 2021-06-18 | 2021-09-14 | 2 | OD | Doug Wenger
smeal Bldg | 00-06709.00 | 202101041 | 543691 | 0976-001 | Building Reno - Revision | C of O | 2021-11-02 | 2022-01-06 | 2 | OD | Doug Wenger
Smeal Bldg | 00-06709.00 | 202101143 | 544124 | 0976-001 | Building Renovations - Fire Alarm | C of O | 2021-11-29 | 2022-01-06 | 2 | OD | Doug Wenger
FAYETTE CAMPUS 0984-000
Eberly | 00-07192.00 | 202100190 | 541867 | 0984-001 | RTU Replacement | Building Permit | 2021-02-08 | 2021-03-15 | 2 | OD | Ron Kobelenske
Library | 00-07192.00 | 202100203 | 541866 | 0984-003 | RTU Replacement | Building Permit | 2021-02-08 | 2021-03-18 | 2 | OD | Ron Kobelenske
FRUIT RESEARCH CENTER 0968-000
GRAPE RESEARCH 0967-000
GREAT VALLEY 0993-000
GREATER ALLEGHENY CAMPUS 0978-000
Frable | 00-07224.00 | 202100234 | 541870 | 0978-004 | 2nd Floor Reno Phase 3 | C of O | 2021-03-24 | 2021-08-19 | 2 | OD | Ron Kobelinski
Frable | 00-07224.00 | 202100761 | 542825 | 0978-004 | 2nd Floor Reno Phase 3 - Sprinkler | C of O | 2021-08-20 | 2021-08-19 | 2 | OD | Ron Kobelinski
Student Union | 00-07233.00 | 202100306 | 542153 | 0978-006 | GASCC Lower Level Game Room Reno | Building Permit |  | 2021-04-05 | 2 | OD
Ostermayer | 00-06375.00 | 202101000 | 543461 | 0978-012 | RTU Access Platform | Building Permit |  | 2021-10-21 | 2 | OD | Ron Kobelinski
HAZLETON CAMPUS 0973-000
Dining Hall | 00-05591.00 |  |  | 0973-010 | Sewer Line Repair | Rejected | 2021-06-17 | 2021-08-11 | 1 | DS/OD | Justin Keister | Mike Rupert
Lofstrom Library | 00-06162.00 | 202100701 | 542719 | 0973-006 | Outdoor Equipment Pad and Enclosure | Building Permit | 2021-06-04 | 2021-08-05 | 2 | OD | Kyle Hollick
Water Service bldg | 00-08161.00 | 202100307 | 542038 | 0973-017 | Upgrade Piping and Equipment | Building Permit | 2021-03-02 | 2021-04-20 | 2 | DS | Kyle Hollick | Adam Davis
HERSHEY 0990-000
Chapel | N/A | 202100570 | 542520 | 0990-001 | New Addition | Building Permit |  | 2021-06-29 | 2 | OD
LEHIGH VALLEY 0977-000
Academic Bldg | 00-08065.00 | 202100173 | 541146 | 0977-100 | Admissions Welcome Center Reno | C of O | 2021-03-11 | 2021-10-27 | 2 | OD | Kyle Hollick
Academic Bldg | 00-06577.00 |  |  | 0977-100 | Relocation of Lion Shrine | Rejected | 2021-07-01 | 2021-08-30 | 2 | DS | Kyle Hollick | Jason McCoy
Academic Bldg | 00-08265.00 | 202100754 | 542801 | 099-100 | IT Offices | Building Permit |  | 2021-08-13 | 2 | OD | Kyle Hollick
MONT ALTO CAMPUS 0970-000
Sawmill Pavilion | 00-08209.00 | 202100596 | 542662 | 0971-117 | Sawmill Pavilion | C of O | 2021-07-07 | 2021-10-07 | 2 | OD | Doug Wenger
NAVY YARD
NEW KENSINGTON 0981-000
Administration Bldg | 00.08106.00 | 202200012 | 544641 | 0981-005 | Abatement | Building Permit | 2021-12-06 | 2022-01-13 | 2 | OD | Marcus Marasco
Science and Tech | 00-08236.00 | 202100873 | 542720 | 0981-009 | Biology Lab Reno | Building Permit |  | 2021-09-16 | 2 | OD
Student Union | 00-00777.00 | 202100189 | 541985 | 0981-007 | Fire Alarm Upgrades - Revision | Building Permit |  | 2021-03-18 | 2 | OD
ROCK SPRINGS 0959-000
SCHUYLKILL CAMPUS 0975-000
Administration Bldg | 00-07329.00 | 202100522 | 542526 | 0975-006 | Office 102-108 Reno | C of O | 2021-06-15 | 2021-11-18 | 2 | OD | Kyle Hollick
Administration Bldg | 00-04876.00 | 202100526 | 542567 | 0975-006 | Addition of Elevator - Fire Alarm | C of O | 2021-06-15 | 2021-12-27 | 2 | OD | Kyle Hollick
Ciletti Memorial Iibrary | 00-07352.00 | 202100110 | 541315 | 0975-003 | Room 120 | C of O |  | 2021-08-05 | 2 | OD | Andy Ritter
Classroom Bldg | 00-07102.00 | 202100191 | 421862 | 0975-005 | Nursing Lab | C of O | 2021-03-15 | 2021-10-19 | 2 | OD | Kyle Hollick
Classroom Bldg | 00-07102.00 | 202100707 | 542736 | 0975-005 | Nursing Lab - Sprinkler | C of O | 2021-08-05 | 2021-10-19 | 2 | OD | Kyle Hollick
Classroom Bldg | 00-07102.00 | 202100834 | 543008 | 0975-005 | Nursing Lab - Fire Alarm | C of O | 2021-09-07 | 2021-10-19 | 2 | OD | Kyle Hollick
Classroom Bldg | 00-07102.00 | 202100868 | 543295 | 0975-005 | Nursing Lab - Revised Sprinkler | C of O | 2021-09-28 | 2021-10-19 | 2 | OD | Kyle Hollick
Student Community Ctr | 00-07402.00 | 202100227 | 541314 | 0975-002 | Morgan Auditorium Stage Extension | Building Permit |  | 2021-03-24 | 2 | OD | Kyle Hollick
SHAVERS CREEK 0960-000
SHENANGO CAMPUS
Forker Lab | 00-06910.00 | 202100127 | 541773 | 0987-001 | Building Renovations - Partial Occupancy | C of O | 2021-01-18 | 2021-03-01 | 2 | OD
WARMINSTER 0998-000
WILKES-BARRE CAMPUS 0983-000
Nittany Courts Classroom Unit B | 00-07328.00 | 202100525 | 542527 | 0983-009 | P & PS Accreditation | Building Permit |  | 2021-06-15 | 2 | OD | Kyle Hollick
Bell Science Bldg | 00-07056.00 | 202100325 | 542162 | 0983-010 | Chiller Replacement Ph 2 | Building Permit |  | 2021-04-12 | 2 | OD | Andy Ritter
SCRANTON CAMPUS 0982-000
Dawson | 00-07198.00 | 202100456 | 542163 | 0982-001 | 2nd Floor HVAC Reno | C of O | 2021-03-29 | 2022-01-25 | 2 | OD | Hollick, Ritter
Dawson | 00-07198.00 | 202100571 | 542733 | 0982-001 | 2nd Floor HVAC Reno -Sprinkler | C of O | 2021-06-29 | 2022-01-25 | 2 | OD | Hollick, Ritter
Dawson | 00-07198.00 | 202100572 | 542732 | 0982-001 | 2nd Floor HVAC Reno -Fire Alarm | C of O | 2021-06-29 | 2022-01-25 | 2 | OD | Hollick, Ritter
Engineering Bldg | 00-06614.00 | 202100159 | 541823 | 0982-086 | Grainger Building - Fire Alarm | C of O | 2021-03-02 | 2021-04-16 | 2 | OD
Sign Permit - by Engineering Bldg | 00-07488.00 | 202101144 | 544125 | 0982-055 | Landmark Sign | Cancelled | 2021-10-25 | 2021-11-29 | 2 | DS | Kyle Hollick | Jason McCoy
Sign Permit - by Engineering Bldg | 00-07488.00 |  |  | 0982-055 | Landmark Sign | Sign Permit | 2022-01-11 |  | 2 | DS | Kyle Hollick | Jason McCoy
Study Learning Ctr | 00-06915.00 | 202100361 | 542210 | 0982-004 | Office Reno Revision | Building Permit |  | 2021-04-18 | 2 | OD | Kyle Hollick
Study Learning Ctr | 00-06915.00 | 202100592 | 542605 | 0982-004 | Door & Signage Revision | C of O | 2021-07-19 | 2022-01-03 | 2 | OD | Kyle Hollick
Study Learning Ctr | 00-06915.00 | 202100711 | 542743 | 0982-004 | Office Reno - Fire Alarm | C of O | 2021-07-28 | 2022-01-03 | 2 | OD | Kyle Hollick
Study Learning Ctr | 00-06915.00 | 202100732 | 542823 | 0982-004 | Office Reno - Partial Occupancy | C of O | 2021-08-05 | 2021-09-21 | 2 | OD | David Parmelee
YORK CAMPUS 0964-000
Main Bldg | 00-08278.00 | 202190673 | 542837 | 0964-001 | Classroom Acoustical and Power Upgrades | C of O | 2021-06-23 | 2022-04-13 | 1 | OD | Doug Wenger
Pullo Ctr | 00-08096.00 | 202100673 | 542665 | 0964-007 | South Building Entrance Repairs | C of O | 2021-07-28 | 2021-10-19 | 2 | OD | Wenger Krause