## Year end close schedule - May
Color Code key: Bold: Central/OPP closing dates Red: Final deadlines |  | 20/21 Fiscal Year End Close Schedule May 2021
Deadline Date | Cutoff Time | Task Completed By | Area | System | Task Description
2021-05-25 | 2:00 P.M. | Abacus Team - Automated | Abacus Team | Abacus Financial | Abacus Financial - Task/Project billings
2021-05-26 | 3:30 P.M. | Staff which enters Shopping carts, Shopping Cart Approvers - OPP Finance (Terri/Kristin), Budget Manager's, and Administrative Support Staff | All of OPP | SIMBA | 20/21 Shopping Carts > $10,000 thru approval workflow and to Procurement Services for processing. Shopping carts may continue to be submitted after this date; however there is no guarantee that a PO will be generated in current FY. **This does also includes submission of carts to increase POs
2021-05-27 | EOD | Jolene Kost | OPP Accounting | Abacus Financial | Send out reminder regarding project and internal contract funding shortfalls

## Year end close schedule - June
Color Code key: Bold: Central/OPP closing/action dates Red: Final deadlines Blue: Abacus Task/Project billing and direct billing cutoff |  | 20/21 Fiscal Year End Close Schedule June 2021
Deadline Date | Cutoff Time | Task Completed By | Area | System | Task Description
2021-06-04 | EOD | Garage Services | Garage Services |  | Garage Services billing (May)
2021-06-06 | EOD | Mary Wellar | OPP Accounting | SIMBA | Review Parked Document Report and provide communication on documents not save a completed
2021-06-07 | EOD | Central | Central Accounting | SIMBA | Central Accounting closes
2021-06-08 | EOD | Mary Wellar | OPP Accounting | Abacus Financial | Email notification to OPP regarding closed status
2021-06-08 | EOD | Mary Wellar | OPP Accounting | SIMBA | Email OPP Stores & Budget Managers <$10,000 Shopping Cart noon deadline (6/17)
2021-06-11 | EOD | Kristin Sykes | OPP Finance | Abacus Financial | Email project and internal contract funding shortfall notifications
2021-06-14 | EOD | Mary Wellar | OPP Accounting | Email | Email Print room (OPP) regarding upcoming direct billing deadline (6/18)
2021-06-14 | EOD | Mary Wellar | OPP Accounting | Email | Email D. Coleman/Beth Pearce refuse/recycling direct billing deadline (6/18)
2021-06-15 | EOD | Mary Wellar | OPP Accounting | SIMBA | Email reminder OPP Stores & Budget Managers <$10,000 Shopping Carts noon deadline (6/17)
2021-06-17 | 12:00 P.M. | Staff which enters Shopping carts, Shopping Cart Approvers - Budget Manager's, Administrative Support Staff, OPP Accounting (Teka/Mary/Beth/Elli) | All of OPP | SIMBA | 20/21 Shopping Carts < $10,000 through departmental approval workflows and received by Procurement Services. Shopping carts may continue to be submitted after this date; however there is no guarantee that a PO will be generated in current FY. **This does also includes submission of carts to increase POs | Procurement Services cut-off 5:00
2021-06-18 | EOD | Jolene Kost | OPP Accounting | Abacus Financial | Print room direct billing
2021-06-18 | EOD | Bing Zhu | OPP Accounting | Abacus Financial | Process received MTIs to date direct billing
2021-06-18 | EOD | Elli Mckenna | OPP Accounting | Abacus Financial | Refuse/Recycling/Compost direct billing
2021-06-18 | EOD | ALL | OPP Accounting | Abacus Financial | Last day to process ANY direct bills (except Garage Services) to be included in June's project/task billings
2021-06-18 | EOD | Kristin Sykes | OPP Finance | Abacus Financial | Send out project and internal contract funding shortfall email notification
2021-06-18 | EOD | Jolene Kost | OPP Accounting | Email | Send reminder email for incinerator billing (Pat Hillard)
2021-06-21 | EOD | Garage Services | Garage Services |  | Garage Services billing (June)
2021-06-24 | 12:00 P.M. | ALL | All of OPP | SIMBA | Last day Procurement Services will accept approved PO change forms (POCF) for existing orders. | Procurement Services cut-off 4:30
2021-06-25 | 12:00 P.M. | All | OPP Accounting | Abacus Financial | All stacks/central transactions processed
2021-06-25 | 2:00 P.M. | Abacus Team | Abacus Team | Abacus Financial | Abacus Financial - Task/Project billings
2021-06-25 | 3:30 P.M. | Penny Aikey | OPP Accounting | General Stores | Final day to purchase items through General Stores - Office Supply Order Processed
2021-06-25 | EOD | Terri Parker/Kristin Sykes | OPP Finance | Abacus Payroll | New charge out rates provided to be added Abacus (must be entered by 6/30 cannot retro)
2021-06-30 | 2:00 P.M. | Staff which enters Shopping carts, Shopping Cart Approvers - Budget Manager's, Administrative Support Staff, OPP Accounting (Teka/Mary/Beth/Elli) | All of OPP | SIMBA | 2020-2021 Catalog Orders through Lion Marketplace must be completely through the departmental approval workflow and orders released.
2021-06-30 | 3:30 P.M. | OPP Stores | OPP Stores | SIMBA | Goods receipt and services rendered through this date are chargeable to the 2020-2021 accounts. Good receipts must be completed by this date to be accounted for appropriately in the current Fiscal Year. Invoices must be received and processed by today for asset purchases. After this date, open 2020-2021 Purchase Orders will be transferred as an encumbrance against 2021- 2022 accounts.

## Year end close schedule - July
Posting date in SIMBA must be changed to 06/30/2021 for any FY 20/21 transactions
Color Code key: Bold: Central/OPP closing/action dates Red: Final deadlines Blue: Abacus Task/Project billing and direct billing cutoff | 20/21 Fiscal Year End Close Schedule July 2021
Deadline Date | Cutoff Time | Task Completed By | Area | System | Task Description
2021-07-01 | EOD | Mary Wellar | OPP Accounting | SIMBA | Network JV ( Bob Puzak allocation)
2021-07-01 | EOD | Kristin Sykes | OPP Finance | SIMBA | Reconciliation of Transfer Cost Centers
2021-07-01 | EOD | Teka Spicer/Mary Wellar | OPP Accounting | SIMBA | Reconciliation of SIMBA IOs
2021-07-01 | EOD | Mary Wellar/Shelby Foster | OPP Accounting | SIMBA | Reconciliation of SIMBA Cash Sales IOs
2021-07-01 |  | Penny Aikey | OPP Accounting |  | Begin pro-rate utility spreadsheet
2021-07-06 | EOD | Mary Wellar | OPP Accounting | SIMBA | Review Parked Document Report and provide communication on documents not save a completed
2021-07-06 | EOD | Mary Wellar/Shelby Foster | OPP Accounting | ABACUS/SIMBA | Utilities DB/Cash Sales (June) to be received from Amy Frantz/Mike Prinkey
2021-07-07 | EOD | ALL | OPP Accounting | ABACUS/SIMBA | Final day to enter Any direct bills for FY 20/21 - Report month June
2021-07-08 | EOD | Mary Wellar | OPP Accounting | SIMBA | Review Parked Document Report and provide communication on documents not save a completed
2021-07-09 | 4:30 P.M. | Chrissy Bowers/Jeri Shultz | Approved by: Terri Parker/Kristin Sykes | SIMBA | 2020-2021 Labor Plan Adjustments - All LD plans needing adjustments must be fully processed
2021-07-09 | 4:30 P.M. | Chrissy Bowers/Jeri Shultz | Approved by: Terri Parker/Kristin Sykes | SIMBA | 2020-2021 Salary Clearing Cost Centers (ending in 00090) must be balanced
2021-07-09 | 4:30 P.M. | Terri Parker | OPP Finance | SIMBA | 2020-2021 Budget Adjustments
2021-07-09 | 12:00 P.M. | ALL | OPP Stores, Kristin, Tracy, Bing and Elli | SAP Concur | All Purchasing Card (PCARD) transactions for 2020-2021 must be completely processed through SAP Concur | SAP Concur deadline 4:30 P.M.
2021-07-09 | 4:30 P.M. | ALL | ALL OPP | SIMBA | All documents must be fully processed and through approval workflow and waiting for Central Desk to approve by 4:30 P.M.
2021-07-12 |  | ALL | OPP Accounting | SIMBA | First day of processing all transactions in new FY - Report month July
2021-07-12 | EOD | Mary Wellar | OPP Accounting | SIMBA | Email notification to OPP regarding closed status
2021-07-14 | EOD | Mary Wellar | OPP Accounting | SIMBA | 634-10 JV/report distribution
2021-07-14 |  | ALL | OPP Accounting | Abacus Financial | Email notification to OPP regarding closed status
2021-07-15 | EOD | Mary Wellar | OPP Accounting | Excel | ARL, Visitor Center, Cost Analysis reports
2021-07-17 | EOD | Mary Wellar | OPP Accounting | Excel | Ian/Erik bldg. maint & custodial info for FY 20/21
2021-07-25 | 2:00 P.M. | Abacus Team | Abacus Team | Abacus Financial | Abacus Financial - Task/Project billings
2021-07-29 |  | Penny Aikey | OPP Accounting |  | Completion of pro-rated Utility Spreadsheet
2021-07-30 | 3:30 P.M. | Terri Parker, Kristin Sykes/Teka Spicer/Mary Wellar | OPP Finance | SIMBA | Tentative Post Close entries in excess of $10K Final review and reconciliation of transfer accounts